## SOURCE DATA
[16 empty] | Enter Date | [5 empty] | 2021-12-01
# | Test Milestone | Test Round | Verticals | Sub-Verticals | Module | Sub-Module | Scenario ID | Scenario Description | Card Type | Test Name (QC Ref) | Test Case Description | Migrated / Synthetic | Interface Dependency | Business Criticality | Expected Results | Batch Dependency | NO.of EOD required | Business DEPT | Plan Run Day | OLD Dates | Plan St Date | Plan End Date | Revised End Date | Completion Date | Test Results | Executed By | Defect ID | SCREEN PRINT (Y/N) | Assigned To | Assigned To - Team | Action | Pending with | Pending with Team | Action Update | Plan Duration | Plan Burnt | Planned % - Till Date | Completion % - Till Date | Complete / Pending | Week # | Completion Week # | Priority
1 | UAT - Apex | Apex Execution R1 | Configuration Module | Configuration | Configuration Module | Merchant Configuration/On boarding | SCN_001 | To validate creation of Commission profile setup |  | TC-001 | To check creation of commission profile setup for Merchant account |  |  |  | Commission profile setup should be successful. Below Configurations should be successful • The Commission Profile Id is the unique number to identify a profile. • The Profile Description. • The Card Scheme. • The Transaction Type • The Commission Type (flat, percentage, percentage and flat, scale). • Flat Amount. • Percentage. • Minimum commission amount. • Maximum commission amount. • The Scale Id that point to the detail ranges information. • Alternate profile details are used to overwrite the original profile details for a predefined period. • Profile Status. |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-17 | PASS | [9 empty] | 1 | 11 | 100% | 100% | Completed | W13 | W23
2 | UAT - Apex | Apex Execution R1 | Configuration Module |  |  |  | SCN_002 | To validate creation of Fee Profile setup |  | TC-002 | To check creation of fee profile setup (Maker and Checker Process) |  |  |  | Fee profile setup should be successful. Below fee should be defined 1- Inactivity fees: In case the merchant fails to perform a defined number of transactions. 2- Installation fees: when the merchant is on boarded 3- Recurring fees: monthly fees • The Fee Profile Id is the unique number to identify a fee profile. • The Profile Description. • Fee code to identify multiple fees per profile. • Fee Amount. • Fee Cycle (M monthly-D daily-W weekly-Q quarterly-Y yearly). • Fee Status (Active, Inactive...). • Valid date period. • Maximum Fee amount |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-28 | PASS |  | BAAP-37 | [7 empty] | 1 | 11 | 100% | 100% | Completed | W13 | W25 | B1&P3
3 | UAT - Apex | Apex Execution R1 | Configuration Module | [6 empty] | TC-003 | To validate customer Pricing category based on user entry • Customer is @ Standard Fees |  |  |  | Standard fees to be applied to the merchant |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-28 | PASS |  | BAAP-37 | [7 empty] | 1 | 11 | 100% | 100% | Completed | W13 | W25 | B1&P3
4 | UAT - Apex | Apex Execution R1 | Configuration Module | [6 empty] | TC-004 | To validate customer Pricing category based on user entry • Customer is @ Discounted Fees |  |  |  | Discounted fees to be applied to the merchant |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-28 | PASS |  | BAAP-37 | [7 empty] | 1 | 11 | 100% | 100% | Completed | W13 | W25 | B1&P3
5 | UAT - Apex | Apex Execution R1 | Configuration Module | [6 empty] | TC-005 | To validate customer Pricing category based on user entry • Customer is @ Waived Fees |  |  |  | Listed fees under Waived fees are not to be applied to the merchant |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-17 | BLOCKED |  | BAAP-37 |  |  |  | Mail sent to receive concurrence from Buisness(Esraa) | Esraa | BSF Business | Details clarified to Business - Awaiting update based on the explanation provided by Maveric | 1 | 11 | 100% | 100% | Pending | W13 | W23 | B1&P3
6 | UAT - Apex | Apex Execution R1 | Merchant Support | Merchant Configuration | Merchant Support Module | Merchant Maintenance | SCN_003 | To validate Bulk Modification for retailer details |  | TC-006 | To validate Bulk Modification for retailer details (CPT, Account, Location,Name,MADA rate, VS rate) by Maker |  |  |  | Retailer details (CPT, Account, Location,Name,MADA rate, VS rate) by Maker should be successful and it should be available in the checker queue |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-17 | BLOCKED |  | BAAP-21 |  |  |  | .EXE Template require for Bulk upload, Modification & Cancellation | Rami | Emcrey | Awaiting standard bulk upload template from EmcREY to retest | 1 | 11 | 100% | 100% | Pending | W13 | W23 | B1&P3
7 | UAT - Apex | Apex Execution R1 | Merchant Support | [6 empty] | TC-007 | To validate Bulk Modification for retailer details (CPT, Account, Location,Name,MADA rate, VS rate) by Approver |  |  |  | Retailer details (CPT, Account, Location,Name,MADA rate, VS rate) by Approver should be successful and it should be reflected accordingly |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-17 | BLOCKED |  | BAAP-21 |  |  |  | .EXE Template require for Bulk upload, Modification & Cancellation | Rami | Emcrey | Awaiting standard bulk upload template from EmcREY to retest | 1 | 11 | 100% | 100% | Pending | W13 | W23 | B1&P3
8 | UAT - Apex | Apex Execution R1 | Merchant Support |  |  |  | SCN_004 | To validate Bulk Cancellation of terminal and retailers |  | TC-008 | To validate Bulk Cancellation of terminal and retailers by Maker |  |  |  | Bulk Cancellation of terminal and retailers by Maker should be successful and available in the checker queue |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-17 | BLOCKED |  | BAAP-21 |  |  |  | .EXE Template require for Bulk upload, Modification & Cancellation | Rami | Emcrey | Awaiting standard bulk upload template from EmcREY to retest | 1 | 11 | 100% | 100% | Pending | W13 | W23 | B1&P3
9 | UAT - Apex | Apex Execution R1 | Merchant Support |  |  |  | SCN_005 | To validate merchant details modification |  | TC-009 | To check changes to the merchant profile is allowed successfully |  |  |  | Listing of commission profile should be edited successful |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-17 | PASS | [9 empty] | 1 | 11 | 100% | 100% | Completed | W13 | W23 | B1&P3
10 | UAT - Apex | Apex Execution R1 | Merchant Support | [6 empty] | TC-010 | To check changes to selected merchant status |  |  |  | Changes made to merchant status should be successful |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-25 | PASS |  | BAAP-05 | [7 empty] | 1 | 11 | 100% | 100% | Completed | W13 | W24 | B1&P3
11 | UAT - Apex | Apex Execution R1 | Merchant Support | [6 empty] | TC-011 | To check changes to merchant address |  |  |  | Changes made to merchant Address should be successful |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-17 | PASS | [9 empty] | 1 | 11 | 100% | 100% | Completed | W13 | W23 | B1&P3
12 | UAT - Apex | Apex Execution R1 | Merchant Support | [6 empty] | TC-012 | To check merchant statement generation via PDF/Excel |  |  |  | Merchant Statement should be generated and available in PDF/Excel |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-17 | FAIL |  | BAAP-16 |  |  |  | Require Open2 Migrated Data - BSF to confirm the ETA for the migration | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 11 | 100% | 100% | Pending | W13 | W23 | B1&P3
13 | UAT - Apex | Apex Execution R1 | Merchant Support | [6 empty] | TC-013 | To check merchant statement generation via Batch file extract |  |  |  | Merchant Statement should be generated via batch outcome |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-17 | BLOCKED |  | BAAP-16 |  |  |  | Require Open2 Migrated Data - BSF to confirm the ETA for the migration | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 11 | 100% | 100% | Pending | W13 | W23 | B1&P3
14 | UAT - Apex | Apex Execution R1 | Merchant Support | [6 empty] | TC-014 | To check closure of merchant account |  |  |  | Merchant account should be closed |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-29 | PASS |  | BAAP-43 | [7 empty] | 1 | 11 | 100% | 100% | Completed | W13 | W25 | B1&P3
15 | UAT - Apex | Apex Execution R1 | Merchant Support |  |  |  | SCN_006 | To validate merchant enquiry |  | TC-015 | To check Enquire the following details, - Merchant General Information. - Merchant Account Information. - Merchant Authorization Details. - Merchant Transaction Details. - Merchant settlement Details. - Merchant Payment Details |  |  |  | Merchant inquiry for following should be listed : - Merchant General Information. - Merchant Account Information. - Merchant Authorization Details. - Merchant Transaction Details. - Merchant settlement Details. - Merchant Payment Details |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-17 | FAIL |  | BAAP-36, BAAP-15 |  |  |  | Business should provide the Data to emcrey to fix the issue. Emcrey should confirm the Enquiry list | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 11 | 100% | 100% | Pending | W13 | W23 | B1&P3
16 | UAT - Apex | Apex Execution R1 | Merchant Support |  |  |  | SCN_007 | To validate Pending retailer creation |  | TC-016 | To check Pending retailer creation during (last hour, today, yesterday, last week, last month) |  |  |  | Retailer details should be displayed and assignee team should be successful in assigning the terminals to the retailer |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-25 | PASS |  | BAAP-12,BAAP-9 | [7 empty] | 1 | 11 | 100% | 100% | Completed | W13 | W24 | B1&P3
17 | UAT - Apex | Apex Execution R1 | Merchant Management | Merchant Management | Merchant Management System | Merchant Inquiry - Merchant Inquiry | SCN_008 | To validate if the system allows to retrieve any detailed information about the merchant |  | TC-017 | To check if the user is able to inquire the merchant details with the valid search criteria |  |  |  | System should display the merchant details successfully |  |  | Functional |  |  | 2021-11-17 | 2021-11-17 |  | 2021-11-17 | PASS | [9 empty] | 1 | 11 | 100% | 100% | Completed | W13 | W23 | B1&P3
18 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-018 | To check if the user is able to inquire the merchant details with the invalid search criteria |  |  |  | System should throw an error |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-17 | PASS | [9 empty] | 1 | 10 | 100% | 100% | Completed | W13 | W23 | B1&P3
19 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-019 | To check if the user is able to view and retrieve any information pertaining to application, account information, address, contacts, terminals, payments & commissions, adjustments & Fees, online transactions for a desired merchant |  |  |  | System should display the merchant details successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-25 | PASS |  | BAAP-36 | [7 empty] | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
20 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Inquiry - Online Transactions | SCN_009 | To validate if the system allows to monitor main the terminal’s transactions and open a case if necessary |  | TC-020 | To check if the user is able to view the online transaction based on the terminal ID |  |  |  | System should display the online transaction successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-17 | BLOCKED |  | BAAP-22 |  |  |  | Require Open2 Migrated Data - BSF to confirm the ETA for the migration | Arsalan/Omer | BSF IT | Require Migrated Terminal Data - Awaiting Approval from Different BSF Departments | 1 | 10 | 100% | 100% | Pending | W13 | W23 | B1&P3
21 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-021 | To check if the user is able to update the record displayed |  |  |  | System should allow the user to update the starting and the ending dates and the refreshing time, and the number of records successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-21 | PASS | [9 empty] | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
22 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Help Desk - Case Management | SCN_010 | To validate if the system allows to manage all open and pending cases related to the merchant’s incidents. |  | TC-022 | To check if the user is able view the all the open and pending cases raised based upon the search criteria as reference |  |  |  | System should display the cases based upon the search criteria successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-24 | PASS |  | BAAP-27 |  |  |  | Emcrey to fix the issue. |  |  |  | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
23 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-023 | To check if the user is able view the all the open and pending cases raised based upon the search criteria as merchant number |  |  |  | System should display the cases based upon the search criteria successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-24 | PASS |  | BAAP-27 |  |  |  | Emcrey to fix the issue. |  |  |  | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
24 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-024 | To check if the user is able view the all the open and pending cases raised based upon the search criteria as terminal id |  |  |  | System should display the cases based upon the search criteria successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-24 | PASS |  | BAAP-27 |  |  |  | Emcrey to fix the issue. |  |  |  | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
25 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-025 | To check if the user is able view the all the open and pending cases raised based upon the search criteria as open date range |  |  |  | System should display the cases based upon the search criteria successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-24 | PASS |  | BAAP-27 |  |  |  | Emcrey to fix the issue. |  |  |  | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
26 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  |  | SCN_011 | To validate if the system allows to manage all add, modify/edit and delete the cases |  | TC-026 | To check if the user is able to select any specific case and to modify/edit it |  |  |  | System should allow the modification successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-24 | PASS |  | BAAP-27 |  |  |  | Emcrey to fix the issue. |  |  |  | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
27 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-027 | To check if the user is able to add a new case |  |  |  | System should allow the new case to be created suessfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-24 | PASS |  | BAAP-27 |  |  |  | Emcrey to fix the issue. |  |  |  | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
28 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-028 | To check if the user is able to remove the cases already added |  |  |  | System should allow the new case to be removed sues fully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-24 | PASS |  | BAAP-27 |  |  |  | Emcrey to fix the issue. |  |  |  | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
29 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-029 | To check if the user is able to view the history of the cases |  |  |  | System should display the case history successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-24 | PASS |  | BAAP-27 |  |  |  | Emcrey to fix the issue. |  |  |  | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
30 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Help Desk - Case Status | SCN_012 | To validate if the system allows to set up case statuses with their relevant descriptions |  | TC-030 | To check if the user is able to view the status of case successfully |  |  |  | System should allow the user to view the status of the of the case successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-24 | PASS |  | BAAP-27 |  |  |  | Emcrey to fix the issue. |  |  |  | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
31 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-031 | To check if the user is able select a case and to modify/edit the status of the case |  |  |  | System should allow the user to modify/edit the case successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-24 | PASS |  | BAAP-27 |  |  |  | Emcrey to fix the issue. |  |  |  | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
32 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-032 | To check if the user is able to delete a status |  |  |  | System should allow the user to delete the status successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-24 | PASS |  | BAAP-27 |  |  |  | Emcrey to fix the issue. |  |  |  | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
33 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Help Desk - Department | SCN_013 | To validate if the system allows to setup the corresponding departments with their emails |  | TC-033 | To check if the user is able to view the existing departments |  |  |  | System should allow the user to view the departments successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-24 | PASS |  | BAAP-27 |  |  |  | Emcrey to fix the issue. |  |  |  | 1 | 10 | 100% | 100% | Completed | W13 | W24 | B1&P3
34 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-034 | To check if the user is able to select any specific department and to modify/edit it |  |  |  | System should allow the user to modify/edit the selected departments successfully |  |  | Functional |  |  | 2021-11-18 | 2021-11-18 |  | 2021-11-29 | PASS |  | BAAP-44 | [7 empty] | 1 | 10 | 100% | 100% | Completed | W13 | W25 | B1&P3
35 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-035 | To check if the user is able to select any department and to delete or remove it |  |  |  | System should allow to delete or remove the department successfully |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-29 | PASS |  | BAAP-27 | [7 empty] | 1 | 9 | 100% | 100% | Completed | W14 | W25 | B1&P3
36 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Help Desk - Issue Type | SCN_014 | To validate if the system allows you to set up issue types needed for creating case incidents while monitoring online transactions. |  | TC-036 | To check if the user is able to view the issue type |  |  |  | System should allow the user to view the issue types |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-17 | PASS | [9 empty] | 1 | 9 | 100% | 100% | Completed | W14 | W23 | B1&P3
37 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-037 | To check if the user is able to select the issue type and to modify/edit it |  |  |  | System should allow the issue type to be modified successfully |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-17 | PASS | [9 empty] | 1 | 9 | 100% | 100% | Completed | W14 | W23 | B1&P3
38 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-038 | To check if the user is able add a new issue type |  |  |  | System should allow the issue type to be added successfully |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-17 | PASS | [9 empty] | 1 | 9 | 100% | 100% | Completed | W14 | W23 | B1&P3
39 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-039 | To check if the user is able remove the new issue type |  |  |  | System should allow the issue type to be removed/deleted successfully |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-17 | PASS | [9 empty] | 1 | 9 | 100% | 100% | Completed | W14 | W23 | B1&P3
40 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Help Desk - Issue Sub Category | SCN_015 | To validate if the system allows to manage the issue subcategory types for a selected issue type. |  | TC-040 | To check if the user is able to view the issue sub category |  |  |  | System should allow the user to view the issue sub category |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-17 | PASS | [9 empty] | 1 | 9 | 100% | 100% | Completed | W14 | W23 | B1&P3
41 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-041 | To check if the user is able to select the issue subcategory and to modify/edit it |  |  |  | System should allow the issue subcategory to be modified successfully |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-17 | PASS | [9 empty] | 1 | 9 | 100% | 100% | Completed | W14 | W23 | B1&P3
42 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-042 | To check if the user is able add a new issue sub category |  |  |  | System should allow the issue sub category to be added successfully |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-17 | PASS | [9 empty] | 1 | 9 | 100% | 100% | Completed | W14 | W23 | B1&P3
43 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-043 | To check if the user is able remove the new issue sub category |  |  |  | System should allow the issue sub category to be removed/deleted successfully |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-17 | PASS | [9 empty] | 1 | 9 | 100% | 100% | Completed | W14 | W23 | B1&P3
44 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Maintenance - Change Merchant Status | SCN_016 | To validate if the system allows to update the status of a merchant |  | TC-044 | To check if the user is able to view the status of the merchant |  |  |  | System should allow the Status of the merchant successfully |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-25 | PASS |  | BAAP-05 | [7 empty] | 1 | 9 | 100% | 100% | Completed | W14 | W24 | B1&P3
45 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-045 | To check if the user is able to select a merchant and to modify/edit the status |  |  |  | System should allow the status modification successfully |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-25 | PASS |  | BAAP-05 | [7 empty] | 1 | 9 | 100% | 100% | Completed | W14 | W24 | B1&P3
46 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Maintenance - Duplicate Merchant | SCN_017 | To validate if the system allows to create a new merchant with the current information of an existing one |  | TC-046 | To check if the user is able to select an existing merchant and insert the required details for creating a duplicate merchant |  |  |  | System should allow the user to create a duplicate merchant |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-23 | PASS |  | BAAP-7,BAAP-33 |  |  |  | Maveric to be retested |  |  |  | 1 | 9 | 100% | 100% | Completed | W14 | W24 | B1&P3
47 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-047 | To check if the user is able to select an existing merchant and insert the invalid details for creating a duplicate merchant |  |  |  | System should throw an error |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-29 | PASS | [9 empty] | 1 | 9 | 100% | 100% | Completed | W14 | W25 | B1&P3
48 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Maintenance - Change Terminal Status | SCN_018 | To validate if the system allows update the terminal status |  | TC-048 | To check if the user is able to view the status of the terminal and to modify/edit it |  |  |  | System should allow the terminal status to be modified successfully |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-25 | PASS |  | BAAP-9,BAAP-22 | [7 empty] | 1 | 9 | 100% | 100% | Completed | W14 | W24 | B1&P3
49 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Maintenance - Terminal Activation | SCN_019 | To validate if the system allows to activates/ deactivates a selected terminal for a specific merchant |  | TC-049 | To check if the user is able to activate the selected terminal for a specific merchant |  |  |  | System should allow the terminal to be activated |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-17 | FAIL |  | BAAP-12,BAAP-9,BAAP-22 |  |  |  | Require Open2 Migrated Data - BSF to confirm the ETA for the migration | Arsalan/Omer | BSF IT | Require Migrated Terminal Data - Awaiting Approval from Different BSF Departments | 1 | 9 | 100% | 100% | Pending | W14 | W23 | B1&P3
50 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-050 | To check if the user is able to deactivate the selected terminal for a specific merchant |  |  |  | System should allow the terminal to be deactivated |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-18 | BLOCKED |  | BAAP-12,BAAP-9,BAAP-22 |  |  |  | Require Open2 Migrated Data - BSF to confirm the ETA for the migration | Arsalan/Omer | BSF IT | Require Migrated Terminal Data - Awaiting Approval from Different BSF Departments | 1 | 9 | 100% | 100% | Pending | W14 | W23 | B1&P3
51 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Maintenance - Hold Payment | SCN_020 | To validate if the system allows to hold the payment |  | TC-051 | To check if the user is able to hold or unhold the amount for a specific merchant by selecting Merchant Pay Hold. |  |  |  | System should hold the amount successfully |  |  | Functional |  |  | 2021-11-21 | 2021-11-21 |  | 2021-11-18 | FAIL |  | BAAP-15 |  |  |  | Business should provide the OPEN2 Data to emcrey to fix the issue. Emcrey should confirm the Enquiry list | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 9 | 100% | 100% | Pending | W14 | W23 | B1&P3
52 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-052 | To check if the user is able to set the release date to release the process. |  |  |  | System should allow the date to be set successfully |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  | 2021-11-18 | BLOCKED |  | BAAP-15 |  |  |  | Business should provide the OPEN2 Data to emcrey to fix the issue. Emcrey should confirm the Enquiry list | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 8 | 100% | 100% | Pending | W14 | W23 | B1&P3
53 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-053 | To check if the user is able to update the hold flag |  |  |  | System should allow the flag to be updated as true/false |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  | 2021-11-18 | BLOCKED |  | BAAP-15 |  |  |  | Business should provide the OPEN2 Data to emcrey to fix the issue. Emcrey should confirm the Enquiry list | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 8 | 100% | 100% | Pending | W14 | W23 | B1&P3
54 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Maintenance - Match Merchant Payment | SCN_021 | To validate if the system allows to display the unmatched merchant payments in reference to a terminal within a range of dates. |  | TC-054 | To check if the user is able to view the list of unmatched merchant payments in reference to a terminal within a range of dates |  |  |  | System should display the unmatched merchant payments in reference to a terminal |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  | 2021-11-18 | BLOCKED |  | BAAP-15 |  |  |  | Business should provide the OPEN2 Data to emcrey to fix the issue. Emcrey should confirm the Enquiry list | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 8 | 100% | 100% | Pending | W14 | W23 | B1&P3
55 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-055 | To check if the user is able to view the list of payments with error and to initiate resending the online payment |  |  |  | System should allow the user to resend the payment for the payment with error |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  | 2021-11-18 | BLOCKED |  | BAAP-15 |  |  |  | Business should provide the OPEN2 Data to emcrey to fix the issue. Emcrey should confirm the Enquiry list | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 8 | 100% | 100% | Pending | W14 | W23 | B1&P3
56 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Statement | SCN_022 | To validate merchant statement |  | TC-056 | To check the merchant statement can be formatted in the following formats -PDF, Excel. |  |  |  | The system should able to generate merchant statements in following formats - PDF, Excel. |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  | 2021-11-18 | BLOCKED |  | BAAP-16 |  |  |  | Require Open2 Migrated Data - BSF to confirm the ETA for the migration | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 8 | 100% | 100% | Pending | W14 | W23 | B1&P3
57 | UAT - Apex | Apex Execution R1 | Security Module | Security Module | Security Module | Entitlement Configuration - Dual Requests | SCN_023 | To validate if the system allows to change his password at any time |  | TC-057 | To check if the user is able to Dual Request showing authorization requests with: action |  |  |  | System should allow the user perform dual request |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  | 2021-11-29 | PASS |  | BAAP-4 | [7 empty] | 1 | 8 | 100% | 100% | Completed | W14 | W25 | B1&P3
58 | UAT - Apex | Apex Execution R1 | Security Module | [6 empty] | TC-058 | To check if the user is able to Dual Request showing authorization requests with: username |  |  |  | System should allow the user perform dual request |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  | 2021-11-29 | PASS |  | BAAP-4 | [7 empty] | 1 | 8 | 100% | 100% | Completed | W14 | W25 | B1&P3
59 | UAT - Apex | Apex Execution R1 | Security Module | [6 empty] | TC-059 | To check if the user is able to Dual Request showing authorization requests with: statuses |  |  |  | System should allow the user perform dual request |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  | 2021-11-29 | PASS |  | BAAP-11,BAAP-6 | [7 empty] | 1 | 8 | 100% | 100% | Completed | W14 | W25 | B1&P3
60 | UAT - Apex | Apex Execution R1 | Security Module | [6 empty] | TC-060 | To check if the user is able to Dual Request showing authorization requests with: request dates |  |  |  | System should allow the user perform dual request |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  | 2021-11-29 | PASS |  | BAAP-11,BAAP-6 | [7 empty] | 1 | 8 | 100% | 100% | Completed | W14 | W25 | B1&P3
61 | UAT - Apex | Apex Execution R1 | Security Module |  |  | Entitlement - Users Sessions | SCN_024 | To validate if the system allows to show all the open and to invalidate the sessions |  | TC-061 | To check if the user is able to view all the open sessions |  |  |  | System should allow the user to view all the sessions |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  | 2021-11-18 | PASS | [9 empty] | 1 | 8 | 100% | 100% | Completed | W14 | W23 | B1&P3
62 | UAT - Apex | Apex Execution R1 | Settlement Process | Settlement and Clearing | Settlement Process Module | Settlement Process Module | SCN_025 | Clearing & Reconciliation |  | TC-062 | Replicate transactions from Open2 System |  |  |  | See the transactions in Inquiry screen of Clearing application Count matching with the count of Open2 EB_TRAN_LOG and Cortex TRANS_LOG |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 8 | 100% | 0% | Pending | W14 |  | B1&P3
63 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-063 | Load Incoming MIGS Files |  |  |  | the transactions are properly populated in TRANS_LOG, MIGS_HDR and MIGS_DTL tables |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 8 | 100% | 0% | Pending | W14 |  | B1&P3
64 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-064 | Load incoming TLF files from SAMA |  |  |  | The data is properly loaded in TLF table |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 8 | 100% | 0% | Pending | W14 |  | B1&P3
65 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-065 | Load incoming EP747 file from VISA after uploading the file to VISA |  |  |  | IPM file generation to include the MasterCard transactions that were received in the incoming DCF file |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 8 | 100% | 0% | Pending | W14 |  | B1&P3
66 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-066 | Load TT068 MasterCard full replacement Bin file (received twice a year) |  |  |  | the corresponding IRD table will be filled |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 8 | 100% | 0% | Pending | W14 |  | B1&P3
67 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-067 | Load TT067 MasterCard BIN file |  |  |  | the corresponding IRD table will be updated |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 8 | 100% | 0% | Pending | W14 |  | B1&P3
68 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-068 | Load incoming TT113 file from MC after uploading the file to MasterCard |  |  |  | the summary should be reflected in MCSETRECON and in case of rejections MCSETREJLOG should be filled |  |  | Functional |  |  | 2021-11-22 | 2021-11-22 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 8 | 100% | 0% | Pending | W14 |  | B1&P3
69 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-069 | Generate outgoing BASE II file |  |  |  | The file should include all the POS and ECOM VISA (local credit and all international) transactions make sure refund and purchase are properly reflected |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 7 | 100% | 0% | Pending | W14 |  | B1&P3
70 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-070 | Generate outgoing IPM file |  |  |  | The file should include all the POS and ECOM MC (local credit and all international) transactions and purchase are properly reflected |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 7 | 100% | 0% | Pending | W14 |  | B1&P3
71 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-071 | Run Merchant Processor |  |  |  | Make sure the payments are generated properly by scheme VISA, MC, mada, GCC, UPI |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 7 | 100% | 0% | Pending | W14 |  | B1&P3
72 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-072 | Generate Posting file |  |  |  | Generate the outgoing posting file to be processed in bank's backend system based on the given events. |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 7 | 100% | 0% | Pending | W14 |  | B1&P3
73 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-073 | Load Response file |  |  |  | Load the response file to reflect the successful processed payments to merchants |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 7 | 100% | 0% | Pending | W14 |  | B1&P3
74 | UAT - Apex | Apex Execution R1 | Settlement Process |  |  |  | SCN_026 | Payments to Merchants |  | TC-074 | Validate the Daily Pay-outs file to Merchants |  |  |  | The payments should get transferred to the merchant account |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 7 | 100% | 0% | Pending | W14 |  | B1&P3
75 | UAT - Apex | Apex Execution R1 | Fees | Fees | Fees | Fees | SCN_027 | Override user entry rates |  | TC-075 | To validate if overriding the user entry rates is possible |  |  |  | Overriding successful for the rate implemented by the user |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  | 2021-11-18 | BLOCKED |  | BAAP-37 |  |  |  | Mail sent to receive concurrence from Buisness(Esraa) | Esraa | BSF Business | Details clarified to Business - Awaiting update based on the explanation provided by Maveric | 1 | 7 | 100% | 100% | Pending | W14 | W23 | B1&P3
76 | UAT - Apex | Apex Execution R1 | Fees |  |  |  | SCN_028 | POS Fees |  | TC-076 | To validate POS Fees for inactive terminal |  |  |  | Charges applied successfully of 100SR |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  | 2021-11-18 | BLOCKED |  | BAAP-37 |  |  |  | Business should provide the updated Fee list to emcrey to fix the issue. | Esraa | BSF Business | Details clarified to Business - Awaiting update based on the explanation provided by Maveric | 1 | 7 | 100% | 100% | Pending | W14 | W23 | B1&P3
77 | UAT - Apex | Apex Execution R1 | Fees |  |  |  | SCN_029 | e-commerce (ePay) fees |  | TC-077 | Setup fee (one time fee) |  |  |  | Monthly Services setup fee should be deducted successfully from Merchant to BSF |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  | 2021-11-18 | BLOCKED |  | BAAP-37 |  |  |  | Business should provide the OPEN2 Data to emcrey to fix the issue. | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 7 | 100% | 100% | Pending | W14 | W23 | B1&P3
78 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-078 | Fraud Fee (one time fee) |  |  |  | Monthly Fraud Fee deducted successfully from Merchant to BSF |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  | 2021-11-18 | BLOCKED |  | BAAP-37 |  |  |  | Business should provide the OPEN2 Data to emcrey to fix the issue. | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 7 | 100% | 100% | Pending | W14 | W23 | B1&P3
79 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-079 | Monthly fee (Fixed amount deducted per month) |  |  |  | Monthly Fees deducted successfully from Merchant to BSF |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  | 2021-11-18 | BLOCKED |  | BAAP-37 |  |  |  | Business should provide the OPEN2 Data to emcrey to fix the issue. | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 7 | 100% | 100% | Pending | W14 | W23 | B1&P3
80 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-080 | Refund Fee: fixed amount per transaction |  |  |  | Monthly Refund Fee deducted successfully from Merchant to BSF |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  | 2021-11-18 | BLOCKED |  | BAAP-37 |  |  |  | Business should provide the OPEN2 Data to emcrey to fix the issue. | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 7 | 100% | 100% | Pending | W14 | W23 | B1&P3
81 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-081 | Chargeback fee: fixed amount per transaction |  |  |  | Monthly Charge back Fee deducted successfully from Merchant to BSF |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  | 2021-11-18 | BLOCKED |  | BAAP-37 |  |  |  | Business should provide the OPEN2 Data to emcrey to fix the issue. | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 7 | 100% | 100% | Pending | W14 | W23 | B1&P3
82 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-082 | Failed transaction fee: fixed amount per transaction |  |  |  | Monthly Failed transaction Fee deducted successfully from Merchant to BSF |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  | 2021-11-18 | BLOCKED |  | BAAP-37 |  |  |  | Business should provide the OPEN2 Data to emcrey to fix the issue. | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 7 | 100% | 100% | Pending | W14 | W23 | B1&P3
83 | UAT - Apex | Apex Execution R1 | Merchant Support | Merchant Support | POS Inventory Module | Stock Management System - Vendor | SCN_030 | To Validate the Branch user is able to enquire and view the list of Vendors |  | TC-083 | To check if the user is able to view vendors list of name in the APEX branch application |  |  |  | List of Vendors name should be allowed for the user to enquire |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  | 2021-11-18 | PASS | [9 empty] | 1 | 7 | 100% | 100% | Completed | W14 | W23 | B1&P3
84 | UAT - Apex | Apex Execution R1 | Merchant Support | [6 empty] | TC-084 | To check if the user is able to search with invalid vendors name in the APEX branch application |  |  |  | System should display the error notification if there are no matching results |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  | 2021-11-18 | FAIL |  | BAAP-38 |  |  |  | .EXE Template require for Bulk upload, Modification & Cancellation | Esraa | BSF Business | Awaiting Esraa to discuss intenally and update | 1 | 7 | 100% | 100% | Pending | W14 | W23 | B1&P3
85 | UAT - Apex | Apex Execution R1 | Merchant Support |  | POS Inventory Module | Stock Management System - Vendor | SCN_031 | To Validate the Branch user is able to Add new Vendors |  | TC-085 | To check if the user is able to add new vendors in the APEX branch application |  |  |  | New vendor creation should be successful and system should display the newly added vendor in the application immediately |  |  | Functional |  |  | 2021-11-23 | 2021-11-23 |  | 2021-11-18 | PASS | [9 empty] | 1 | 7 | 100% | 100% | Completed | W14 | W23 | B1&P3
86 | UAT - Apex | Apex Execution R1 | Merchant Support |  |  |  | SCN_032 | To Validate the Branch user is able to remove the existing Vendors |  | TC-086 | To check if the user is able to remove the vendors in the APEX branch application |  |  |  | Removal of existing vendors should be successful and system should not display the removed vendor in the list |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-23 | PASS |  | BAAP-39,BAAP-22 |  |  |  | Maveric to be retested |  |  |  | 1 | 6 | 100% | 100% | Completed | W14 | W24 | M
87 | UAT - Apex | Apex Execution R1 | Merchant Support | [6 empty] | TC-087 | To check if user is able to add a vendor that was removed earlier |  |  |  | System should allow the user to add the vendor that was removed |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-23 | PASS |  | BAAP-39,BAAP-22 |  |  |  | Maveric to be retested |  |  |  | 1 | 6 | 100% | 100% | Completed | W14 | W24 | M
88 | UAT - Apex | Apex Execution R1 | Merchant Support |  |  | Stock Management System - Brand | SCN_033 | To Validate the Branch user is able to add/modify/enquire/remove and view the linked brands for selected vendors |  | TC-088 | To check if the user is able to view the brands in the APEX branch application |  |  |  | System should display the linked brands for selected vendors |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-18 | PASS | [9 empty] | 1 | 6 | 100% | 100% | Completed | W14 | W23 | B1&P3
89 | UAT - Apex | Apex Execution R1 | Merchant Support | [6 empty] | TC-089 | To check if the user is able to modify the brands with linked vendors in the APEX branch application |  |  |  | Modify of brands should be successful and displayed |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-18 | PASS | [9 empty] | 1 | 6 | 100% | 100% | Completed | W14 | W23 | B1&P3
90 | UAT - Apex | Apex Execution R1 | Merchant Support |  |  | Stock Management - POS Inventory | SCN_034 | To Validate the Branch user is able to enquire and edit the POS inventory details |  | TC-090 | To check if the user is able to modify the POS inventory in the APEX branch application |  |  |  | System should display the modified POS inventory details |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-23 | PASS |  | BAAP-22 |  |  |  | Require Open2 Migrated Data - BSF to confirm the ETA for the migration |  |  |  | 1 | 6 | 100% | 100% | Completed | W14 | W24 | B1
91 | UAT - Apex | Apex Execution R1 | Merchant Support | [6 empty] | TC-091 | To check if the user is able to remove the POS inventory in the APEX branch application |  |  |  | Removal of POS Inventory should be successful and should not be displayed |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-23 | PASS |  | BAAP-22 |  |  |  | Require Open2 Migrated Data - BSF to confirm the ETA for the migration |  |  |  | 1 | 6 | 100% | 100% | Completed | W14 | W24 | B1
92 | UAT - Apex | Apex Execution R1 | Terminal Management | Terminal Management System | Terminal Management System | Terminal Management System- Merchant Application | SCN_035 | To Validate the Branch user is able to modify the Merchant application |  | TC-092 | To check if the user is able to modify on the Merchant desired application in the APEX branch application |  |  |  | System should display the modified merchant application successfully |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-17 | PASS | [9 empty] | 1 | 6 | 100% | 100% | Completed | W14 | W23 | B1
93 | UAT - Apex | Apex Execution R1 | Terminal Management | [6 empty] | TC-093 | To check if user is able to modify the Entity level hierarchy |  |  |  | Entity level changes should be successful and it should specify the rank within its hierarchy |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-25 | PASS |  | BAAP-41 | [7 empty] | 1 | 6 | 100% | 100% | Completed | W14 | W24 | M
94 | UAT - Apex | Apex Execution R1 | Terminal Management |  |  |  | SCN_036 | To validate the Entity level changes |  | TC-094 | To check if user is able to set a Entity level hierarchy |  |  |  | Entity level changes should be successful and it should specify the rank within its hierarchy |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-25 | PASS |  | BAAP-41 | [7 empty] | 1 | 6 | 100% | 100% | Completed | W14 | W24 | M
95 | UAT - Apex | Apex Execution R1 | Terminal Management | [6 empty] | TC-095 | To check if the entity level is defined from highest to lowest |  |  |  | Levels should be defined from highest to lowest starting at Level One |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-25 | PASS |  | BAAP-41 | [7 empty] | 1 | 6 | 100% | 100% | Completed | W14 | W24 | M
96 | UAT - Apex | Apex Execution R1 | Terminal Management |  |  |  | SCN_037 | To Validate the Branch user is able to add new Merchant application |  | TC-096 | To check if the user is able to add a new Merchant application in the APEX branch application |  |  |  | System should display the newly added application successfully New Merchant number should be generated |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-18 | PASS | [9 empty] | 1 | 6 | 100% | 100% | Completed | W14 | W23 | B1
97 | UAT - Apex | Apex Execution R1 | Terminal Management | [6 empty] | TC-097 | To check if merchant definition is successful through bulk upload with the standard file format |  |  |  | Merchant definition through bulk upload file should be successful New Merchant number should be generated |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-18 | BLOCKED |  | BAAP-21 |  |  |  | .EXE Template require for Bulk upload, Modification & Cancellation | Rami | Emcrey | Awaiting standard bulk upload template from EmcREY to retest | 1 | 6 | 100% | 100% | Pending | W14 | W23 | B1
98 | UAT - Apex | Apex Execution R1 | Terminal Management |  |  |  | SCN_038 | To Validate the Branch user is able to remove terminal |  | TC-098 | To check whether the user is able to do (flag a terminal as removed) click on Delete Terminal option in the APEX branch application. |  |  |  | Removal of terminal should be successful and should not be displayed |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-29 | FAIL |  | BAAP-45 |  |  |  |  | Rami | Emcrey | Awaiting defect fix by eMcREY | 1 | 6 | 100% | 100% | Pending | W14 | W25 | B1
99 | UAT - Apex | Apex Execution R1 | Terminal Management |  |  |  | SCN_039 | To Validate the Branch user is able to replace terminal |  | TC-099 | To check whether the user can able to do (flag a terminal as replace) click on Replace Terminal to replace a newly assigned terminal with a removed terminal. in the APEX branch application. |  |  |  | Replacement of terminal should be successful |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-18 | BLOCKED |  | BAAP-45 |  |  |  | Require Open2 Migrated Data - BSF to confirm the ETA for the migration | Rami | Emcrey | Awaiting defect fix by eMcREY | 1 | 6 | 100% | 100% | Pending | W14 | W23 | B1
100 | UAT - Apex | Apex Execution R1 | Terminal Management |  |  |  | SCN_040 | To Validate the Branch user is able to Change Terminal Status |  | TC-100 | To check whether the user can able to change the terminal status in the APEX branch application. |  |  |  | System should display the changed terminal status successfully |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-25 | PASS |  | BAAP-22 | [7 empty] | 1 | 6 | 100% | 100% | Completed | W14 | W24 | B1
101 | UAT - Apex | Apex Execution R1 | Terminal Management |  |  |  | SCN_041 | To Validate the Branch user is able to approve the merchant application |  | TC-101 | To check if user is able to approve the merchant application through the merchant application management screen |  |  |  | System should allow user to approve the merchant application successfully through merchant applicant management system |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-18 | PASS | [9 empty] | 1 | 6 | 100% | 100% | Completed | W14 | W23 | B1
102 | UAT - Apex | Apex Execution R1 | Terminal Management |  |  |  | SCN_042 | To Validate the Branch user is able to reject the application on the Merchant application management screen |  | TC-102 | To check if user is able to reject the merchant application through the merchant application management screen |  |  |  | System should allow user to reject the merchant application successfully through merchant applicant management system |  |  | Functional |  |  | 2021-11-24 | 2021-11-24 |  | 2021-11-18 | PASS | [9 empty] | 1 | 6 | 100% | 100% | Completed | W14 | W23 | B1
103 | UAT - Apex | Apex Execution R1 | Terminal Management |  | Terminal Management System | Terminal Management System- Account Type | SCN_043 | To Validate the Branch user is able to add/modify /remove/enquire the Account Type |  | TC-103 | To check if the user is able to click on the Account Type and enquire in the APEX branch application |  |  |  | System should display the list of account type successfully |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-24 | PASS | [9 empty] | 1 | 5 | 100% | 100% | Completed | W14 | W24 | B1
104 | UAT - Apex | Apex Execution R1 | Terminal Management | [6 empty] | TC-104 | To check if the user is able to modify/Edit on the Account Type in the APEX branch application |  |  |  | System should allow user to modify the account type successfully and display accordingly |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-12-01 | NOT_APPLICABLE |  | BAAP-40 | [7 empty] | 1 | 5 | 100% | 100% | Pending | W14 | W25 | B1
105 | UAT - Apex | Apex Execution R1 | Terminal Management | [6 empty] | TC-105 | To check if the user is able to add a Account Type in the APEX branch application |  |  |  | Addition of account type should be successful |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-12-01 | NOT_APPLICABLE |  | BAAP-40 | [7 empty] | 1 | 5 | 100% | 100% | Pending | W14 | W25 | B1
106 | UAT - Apex | Apex Execution R1 | Terminal Management | [6 empty] | TC-106 | To check if the user is able to remove the Account Type in the APEX branch application |  |  |  | Removal of account type should be successful |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-12-01 | NOT_APPLICABLE |  | BAAP-40 | [7 empty] | 1 | 5 | 100% | 100% | Pending | W14 | W25 | B1
107 | UAT - Apex | Apex Execution R1 | Merchant Management | Merchant management system | Merchant management system | Merchant Reconciliation - Multi Currency support | SCN_044 | To validate if the system allows multi currency accounts to be associated to the merchant. |  | TC-107 | To check if the user is able to receive payments from multi currency accounts |  |  |  | System should allow payments from (USD, SAR, EUR and GBP) accounts |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-18 | BLOCKED |  | BAAP-15 |  |  |  | Business should provide the OPEN2 Data to emcrey to fix the issue. | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 5 | 100% | 100% | Pending | W14 | W23 | B1
108 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant and Terminal Details | SCN_045 | To validate if the system allows to capture the merchant and terminal details |  | TC-108 | To check if the user is able capture the Merchant Retailer Id |  |  |  | System should allow capture the Merchant Retailer Id, which is a unique number, generated for a new merchant following the SAMA specifications. |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-25 | PASS | [9 empty] | 1 | 5 | 100% | 100% | Completed | W14 | W24 | B1
109 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  |  | SCN_046 | To validate if the system allows to capture the merchant and terminal details |  | TC-109 | To check if the user is able capture The Terminal id |  |  |  | System should allow to capture the Terminal id defined under the merchant selected from the available terminals in stock database |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-25 | PASS |  | BAAP-22 | [7 empty] | 1 | 5 | 100% | 100% | Completed | W14 | W24 | B1
110 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-110 | To check if the user is able capture the Entity Level defines the hierarchy level available for setting Acquiring Entity |  |  |  | System should allow to capture the Entity Level defining the hierarchy levels |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-25 | PASS |  | BAAP-41 | [7 empty] | 1 | 5 | 100% | 100% | Completed | W14 | W24 | P1
111 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  |  | SCN_047 | To validate if the system allows to capture the details based on the highest level on hierarchy to the lowest levels |  | TC-111 | To check if the user is able to define the details based on the Merchant name |  |  |  | System should allow to define the level based on the hierarchy levels |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-25 | PASS |  | BAAP-41 | [7 empty] | 1 | 5 | 100% | 100% | Completed | W14 | W24 | P1
112 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-112 | To check if the user is able to define the details based on the shop name |  |  |  | System should allow to define the level based on the hierarchy levels |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-25 | PASS |  | BAAP-41 | [7 empty] | 1 | 5 | 100% | 100% | Completed | W14 | W24 | P1
113 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-113 | To check if the user is able to define the details based on the Merchant Category Code |  |  |  | System should allow to define the level based on the hierarchy levels |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-25 | PASS |  | BAAP-41 | [7 empty] | 1 | 5 | 100% | 100% | Completed | W14 | W24 | P1
114 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-114 | To check if the user is able to define the details based on the Merchant Type |  |  |  | System should allow to define the level based on the hierarchy levels |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-28 | PASS |  | BAAP-41 | [7 empty] | 1 | 5 | 100% | 100% | Completed | W14 | W25 | P1
115 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-115 | To check if the user is able to define the details based the Economic activity |  |  |  | System should allow to define the level based on the hierarchy levels |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-28 | PASS |  | BAAP-41 | [7 empty] | 1 | 5 | 100% | 100% | Completed | W14 | W25 | P1
116 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-116 | To check if the user is able to define the details based on the Registration Number |  |  |  | System should allow to define the level based on the hierarchy levels |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-28 | PASS |  | BAAP-41 | [7 empty] | 1 | 5 | 100% | 100% | Completed | W14 | W25 | P1
117 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-117 | To check if the user is able to define the details based on the Risk Level |  |  |  | System should allow to define the level based on the hierarchy levels |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-25 | PASS |  | BAAP-41 | [7 empty] | 1 | 5 | 100% | 100% | Completed | W14 | W24 | P1
118 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-118 | To check if the user is able to define the details based on the Contract Expiry Date |  |  |  | System should allow to define the level based on the hierarchy levels |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-21 | BLOCKED |  | BAAP-41 |  |  |  | Mail sent to receive concurrence from Buisness(Esraa) | Esraa | BSF Business | Query raised to Business Awaiting update | 1 | 5 | 100% | 100% | Pending | W14 | W24 | P1
119 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-119 | To check if the user is able to define the details based on the Allowed Card Scheme |  |  |  | System should allow to define the level based on the hierarchy levels |  |  | Functional |  |  | 2021-11-25 | 2021-11-25 |  | 2021-11-28 | PASS |  | BAAP-41 | [7 empty] | 1 | 5 | 100% | 100% | Completed | W14 | W25 | P1
120 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-120 | To check if the user is able to define the details based on the Fee Waiver Flag |  |  |  | System should allow to define the level based on the hierarchy levels |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  | 2021-11-21 | BLOCKED |  | BAAP-41 |  |  |  | Emcrey to clarify on hierarchy & entity level | Esraa | BSF Business | Details clarified to Business - Awaiting update based on the explanation provided by Maveric | 1 | 4 | 100% | 100% | Pending | W15 | W24 | P1
121 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-121 | To check if the user is able to define the details based on the promoter |  |  |  | System should allow to define the level based on the hierarchy levels |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  | 2021-11-25 | PASS |  | BAAP-41 | [7 empty] | 1 | 4 | 100% | 100% | Completed | W15 | W24 | P1
122 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  |  | SCN_048 | To validate if the system allows to include all the financial information |  | TC-122 | To check if the user is able to calculate the fees for the payments made |  |  |  | System should allow to validate accounts and should calculate the fees accordingly |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 4 | 100% | 0% | Pending | W15
123 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-123 | To check if the user is able to calculate the commissions for the payments made |  |  |  | System should allow to validate accounts and should calculate the commissions accordingly |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 4 | 100% | 0% | Pending | W15
124 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-124 | To check if the user is able to calculate the amount to be posted to the merchant banking account |  |  |  | System should allow the validate accounts and should calculate the amount accordingly |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 4 | 100% | 0% | Pending | W15
125 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  |  | SCN_049 | To validate if the Maker checker is configured |  | TC-125 | To check if the user is able to initiate a approval request as a maker |  |  |  | Maker profile has to be configured successfully and the system should allow to initiate the approval request |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  | 2021-11-17 | PASS | [9 empty] | 1 | 4 | 100% | 100% | Completed | W15 | W23
126 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-126 | To check if the user is able to approve the request online as a checker |  |  |  | Checker profile has to be configured successfully and the system should allow request to be approved online |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  | 2021-11-17 | PASS | [9 empty] | 1 | 4 | 100% | 100% | Completed | W15 | W23
127 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-127 | To check if the checker user is able to approve the request offline as a checker |  |  |  | Checker profile has to be configured successfully and the system should allow request to be approved offline |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  | 2021-11-21 | BLOCKED |  | BAAP-18 |  |  |  | Emcrey to enable the dual request | Maveric | Maveric | In Progress | 1 | 4 | 100% | 100% | Pending | W15 | W24 | P1
128 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  |  | SCN_050 | To validate if the system allows the user to create and manage merchant Addresses |  | TC-128 | To check if the user is able to create new merchant addresses |  |  |  | System should allow to create the new merchant addresses |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  | 2021-11-18 | PASS | [9 empty] | 1 | 4 | 100% | 100% | Completed | W15 | W23
129 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-129 | To check if the user is able to manage merchant addresses |  |  |  | System should allow to manage the merchant addresses |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  | 2021-11-18 | PASS | [9 empty] | 1 | 4 | 100% | 100% | Completed | W15 | W23
130 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-130 | To check if the user is able to assign the roles , such as: POS Location, Reporting, Shipping, Billing, etc. |  |  |  | System should allow the user to assign the roles such as Reporting, Shipping, Billing, etc. |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  | 2021-11-21 | PASS | [9 empty] | 1 | 4 | 100% | 100% | Completed | W15 | W24
131 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-131 | To check if the user is able to have at least one contact information in the address |  |  |  | System should allow to add at least one contact information |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  | 2021-11-18 | PASS | [9 empty] | 1 | 4 | 100% | 100% | Completed | W15 | W23
132 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-132 | To check if the user is able to enter a new contact person for the merchant or select an existing contact from the contact list |  |  |  | System should allow to enter a new contact person the from the contact list |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  | 2021-11-18 | PASS | [9 empty] | 1 | 4 | 100% | 100% | Completed | W15 | W23
133 | UAT - Apex | Apex Execution R1 | Network Reconciliation | Network Reconciliation | Network Reconciliation | Interface file(Outgoing file) | SCN_051 | To validate the Generating Open2 files |  | TC-133 | To check whether Generating Open2 files extracted |  |  |  | Generating Open2 files should be extracted successfully |  |  | Functional |  |  | 2021-11-28 | 2021-11-28 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 4 | 100% | 0% | Pending | W15
134 | UAT - Apex | Apex Execution R1 | Configuration Module | Configuration | Configuration | Merchant Configuration | SCN-052 | To validate merchant hierarchy components configuration module |  | TC-134 | To check whether the following details/components are configured for a new merchant creation to be successful • Institution. • Institution Type. • Master Address. • Institution Contact. • Master Contact. • Language. • Currency code. • Currency rates. • Country, county, province, city and district. • Card Scheme. • Merchant types. • Merchant Category Codes. • General Parameter |  |  |  | The system should be configured with the following components for a new merchant on boarding to be successful • Institution. • Institution Type. • Master Address. • Institution Contact. • Master Contact. • Language. • Currency code. • Currency rates. • Country, county, province, city and district. • Card Scheme. • Merchant types. • Merchant Category Codes. • General Parameter. |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  | 2021-11-30 | PASS | [9 empty] | 1 | 3 | 100% | 100% | Completed | W15 | W25
135 | UAT - Apex | Apex Execution R1 | Configuration Module |  |  | POS Inventory Configuration | SCN-053 | To validate the configuration as part of the inventory module |  | TC-135 | To check whether the following details are configured as part of the inventory module to track the POS device Stock • Vendor • Brand. • POS inventory |  |  |  | The following details should be configured as part of the inventory module to track the POS device Stock • Vendor • Brand. • POS inventory |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  | 2021-11-30 | PASS | [9 empty] | 1 | 3 | 100% | 100% | Completed | W15 | W25
136 | UAT - Apex | Apex Execution R1 | Configuration Module |  |  |  | SCN-054 | To validate adding a new stock |  | TC-136 | To check if user is allowed to add a new stock to the database through the form by entering the required details |  |  |  | System should allow the user to add a new stock to the database through the form by entering all the required details successfully |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 3 | 100% | 0% | Pending | W15
137 | UAT - Apex | Apex Execution R1 | Configuration Module | [6 empty] | TC-137 | To check if system allows the user to add a new stock through file upload with the following details, Terminal ID Terminal Ser NO Terminal Type Terminal Code Vender ID Vendor Name Brand Name Software Version |  |  |  | System should allow the user to add a new stock through file upload successfully with the following details Terminal ID Terminal Ser NO Terminal Type Terminal Code Vender ID Vendor Name Brand Name Software Version |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 3 | 100% | 0% | Pending | W15
138 | UAT - Apex | Apex Execution R1 | Configuration Module |  |  | Commission Configuration | SCN-055 | To validate the configuration of the Commission profile |  | TC-138 | To check whether the following details are configured as part of the Commission profile • The Commission Profile Id • The Profile Description. • The Card Scheme. • The Transaction Type • The Commission Type (flat, percentage, percentage and flat, scale). • Flat Amount. • Percentage. • Minimum commission amount. • Maximum commission amount. • The Scale Id that point to the detail ranges information. • Alternate profile details are used to overwrite the original profile details for a predefined period. • Profile Status. |  |  |  | The following details should be configured as part of the Commission profile • The Commission Profile Id • The Profile Description. • The Card Scheme. • The Transaction Type • The Commission Type (flat, percentage, percentage and flat, scale). • Flat Amount. • Percentage. • Minimum commission amount. • Maximum commission amount. • The Scale Id that point to the detail ranges information. • Alternate profile details are used to overwrite the original profile details for a predefined period. • Profile Status. |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  | 2021-11-30 | PASS | [9 empty] | 1 | 3 | 100% | 100% | Completed | W15 | W25
139 | UAT - Apex | Apex Execution R1 | Configuration Module |  |  | Fee Configuration | SCN-056 | To validate the configuration of the Fee profile |  | TC-139 | To check whether the following details are configured as part of the Fee profile 1- Inactivity fees: In case the merchant fails to perform a defined number of transactions. 2- Installation fees: when the merchant is on boarded 3- Recurring fees: monthly fees • The Fee Profile Id is the unique number to identify a fee profile. • The Profile Description. • Fee code to identify multiple fees per profile. • Fee Amount. • Fee Cycle (M monthly-D daily-W weekly-Q quarterly-Y yearly). • Fee Status (Active, Inactive...). • Valid date period. • Maximum Fee amount |  |  |  | The following details should be configured as part of the Fee profile 1- Inactivity fees: In case the merchant fails to perform a defined number of transactions. 2- Installation fees: when the merchant is on boarded 3- Recurring fees: monthly fees • The Fee Profile Id is the unique number to identify a fee profile. • The Profile Description. • Fee code to identify multiple fees per profile. • Fee Amount. • Fee Cycle (M monthly-D daily-W weekly-Q quarterly-Y yearly). • Fee Status (Active, Inactive...). • Valid date period. • Maximum Fee amount |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  | 2021-11-30 | PASS | [9 empty] | 1 | 3 | 100% | 100% | Completed | W15 | W25
140 | UAT - Apex | Apex Execution R1 | Merchant Onboarding | Merchant On boarding | On boarding | Merchant On boarding | SCN-057 | To validate New merchant profile on boarding |  | TC-140 | To check whether user is able to create application for new BSF merchant with the following appropriate details Retailer Name Arabic Retailer Name Account Debit Account Credit Customer Number Branch MCC City Arabic City Address Arabic Address Terminal type Vendor Connectivity Type Mada % Cap Rate Card % No of Terminals Subgroup Retailer ID Retailer ID Mobile Mobile2 Phone Phone2 Email1 Email2 Fax PO Box Address Line1 Address Line2 Zip Code |  |  |  | - The system should allow the user to create application for a new BSF merchant with the following appropriate details successfully. '- New Merchant number should be generated as per SAMA Specifications Retailer Name Arabic Retailer Name Account Debit Account Credit Customer Number Branch MCC City Arabic City Address Arabic Address Terminal type Vendor Connectivity Type Mada % Cap Rate Card % No of Terminals Subgroup Retailer ID Retailer ID Mobile Mobile2 Phone Phone2 Email1 Email2 Fax PO Box Address Line1 Address Line2 Zip Code |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  | 2021-11-17 | PASS | [9 empty] | 1 | 3 | 100% | 100% | Completed | W15 | W23
141 | UAT - Apex | Apex Execution R1 | Merchant Onboarding | [6 empty] | TC-141 | To check if user is able to create new merchant application through bulk upload in APEX using the standard template with the following details Retailer Name Arabic Retailer Name Account Debit Account Credit Customer Number Branch MCC City Arabic City Address Arabic Address Terminal type Vendor Connectivity Type Mada % Cap Rate Card % No of Terminals Subgroup Retailer ID Retailer ID Mobile Mobile2 Phone Phone2 Email1 Email2 Fax PO Box Address Line1 Address Line2 Zip Code |  |  |  | The system should allow the user to create merchant application through bulk upload using the standard template successfully * New unique merchant IDs should be created as per SAMA Specifications Retailer Name Arabic Retailer Name Account Debit Account Credit Customer Number Branch MCC City Arabic City Address Arabic Address Terminal type Vendor Connectivity Type Mada % Cap Rate Card % No of Terminals Subgroup Retailer ID Retailer ID Mobile Mobile2 Phone Phone2 Email1 Email2 Fax PO Box Address Line1 Address Line2 Zip Code |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  | 2021-11-17 | FAIL |  | BAAP-21, BAAP-33, BAAP-31 |  |  |  |  | Rami | Emcrey | Awaiting standard bulk upload template from EmcREY to retest | 1 | 3 | 100% | 100% | Pending | W15 | W23
142 | UAT - Apex | Apex Execution R1 | Merchant Onboarding | [6 empty] | TC-142 | To check whether the system allows the user to upload the fields with invalid fields |  |  |  | The user should not allow to upload file with invalid fields for a new merchant creation |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  | 2021-11-30 | BLOCKED |  | BAAP-21 |  |  |  |  | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 3 | 100% | 100% | Pending | W15 | W25
143 | UAT - Apex | Apex Execution R1 | Merchant Onboarding | [6 empty] | TC-143 | To check whether the system allows the user to upload the file with incorrect format |  |  |  | The user should not be allowed to upload file with incorrect file format for a new merchant creation |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  | 2021-11-30 | FAIL |  | BAAP-47 |  |  |  |  | Rami | Emcrey | Awaiting defect fix by eMcREY | 1 | 3 | 100% | 100% | Pending | W15 | W25
144 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  | Merchant Management | SCN-058 | To validate the various details of the existing on newly on boarded merchant |  | TC-144 | To check if the Terminal Id is defined for a selected merchant from the available stock database |  |  |  | Terminal Id should be defined for a merchant from the available stock database while it is created |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 3 | 100% | 0% | Pending | W15
145 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-145 | To check if entity levels are defined from highest to lowest to set the Acquiring Entity Hierarchies |  |  |  | Acquiring Entity rank should be specified successfully based on the entity level definition within its hierarchy |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 3 | 100% | 0% | Pending | W15
146 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-146 | To check if account details are attached to the merchant level |  |  |  | System should allow user to attach the account details to the merchant level |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 3 | 100% | 0% | Pending | W15
147 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-147 | To check if the account details are attached at the terminal level |  |  |  | System should allow user to attach the account details to the Terminal level |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 3 | 100% | 0% | Pending | W15
148 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-148 | To check if system allows the user to set a risk level for a merchant |  |  |  | System should allow user to set a risk level for a merchant to indicate the sub status of the merchant |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  | 2021-11-30 | PASS | [9 empty] | 1 | 3 | 100% | 100% | Completed | W15 | W25
149 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-149 | To check if system allows the user to set the Fee waiver flag to yes |  |  |  | Fee should not be calculated if the flag is set to yes for a merchant |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 3 | 100% | 0% | Pending | W15
150 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-150 | To check if system allows the user to set the Fee waiver flag to No |  |  |  | Fee should be calculated if the flag is set to No for a merchant |  |  | Business - Maveric |  |  | 2021-11-29 | 2021-11-29 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 3 | 100% | 0% | Pending | W15
151 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-151 | To check is system allows the user to specify the allowed card scheme on a merchant terminal |  |  |  | System should allow only the specified card scheme on a merchant terminal if defined |  |  | Business - Maveric |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
152 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-152 | To check If system allows the user to modify the Contract Start and End date of a merchant |  |  |  | System should allow user to modify the Contract start and end date of a merchant |  |  | Business - Maveric |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
153 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-153 | To check if system allows the user to inquire/modify the following account details of a merchant • The Account Number • The Account Description. • The Account Currency Code • The Scheme linked to the account. • Bank Number and Name. • Branch Number and Name. • Commission profile • Fee Profile |  |  |  | System should allow the user to inquire/modify the following account details of a merchant • The Account Number • The Account Description. • The Account Currency Code • The Scheme linked to the account. • Bank Number and Name. • Branch Number and Name. • Commission profile • Fee Profile |  |  | Business - Maveric |  |  | 2021-11-30 | 2021-11-30 |  | 2021-11-30 | PASS | [9 empty] | 1 | 2 | 100% | 100% | Completed | W15 | W25
154 | UAT - Apex | Apex Execution R1 | Terminal Management | Terminal Management |  | Terminal Management | SCN-059 | To validate terminal linkage to a merchant and different terminal statuses |  | TC-154 | To check whether terminal linkage is done to the merchant profile with only the Free/Available status terminals |  |  |  | The system should allow the user to link the terminal to the merchant profile. Only the Free/Available status terminal should be listed for the linkage Terminal status should be changed to Reserved/Assigned after the linkage is done successfully |  |  | Business - Maveric |  |  | 2021-11-30 | 2021-11-30 |  | 2021-11-29 | FAIL |  | BAAP-46 |  |  |  |  | Rami | Emcrey | Awaiting defect fix by eMcREY | 1 | 2 | 100% | 100% | Pending | W15 | W25
155 | UAT - Apex | Apex Execution R1 | Terminal Management | [6 empty] | TC-155 | To check if a file is sent to the vendor as a notification to install it once Assigned/Reserved |  |  |  | A file to be sent to the vendor to notify for installation after Assigned/Reserved status is changed |  |  | Business - Maveric |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
156 | UAT - Apex | Apex Execution R1 | Terminal Management | [6 empty] | TC-156 | To check whether the system allows to define additional terminal status |  |  |  | Additional terminal details should be allowed to be defined |  |  | Business - Maveric |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
157 | UAT - Apex | Apex Execution R1 | Terminal Management |  |  | POS Support | SCN-060 | To validate POS inventory details and Merchant support action |  | TC-157 | To check whether the user is able to see the available POS devices. |  |  |  | The system should allow the user to view the available POS devices. |  |  | Business - Maveric |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
158 | UAT - Apex | Apex Execution R1 | Terminal Management | [6 empty] | TC-158 | To check if system allows the user to inquire the following details as part of POS Support/helpdesk division • Merchant General Information. • Merchant Account Information. • Merchant Authorization Details. • Merchant Transaction Details. • Merchant settlement Details. • Merchant Payment Details |  |  |  | System should allow the user to inquire the following details as part of POS Support/helpdesk division • Merchant General Information. • Merchant Account Information. • Merchant Authorization Details. • Merchant Transaction Details. • Merchant settlement Details. • Merchant Payment Details |  |  | Business - Maveric |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
159 | UAT - Apex | Apex Execution R1 | Merchant Onboarding | Merchant On boarding -Business | Merchant On boarding -Business | Merchant Application creation | SCN-061 | To check if the user is able to create a merchant with only access to MADA |  | TC-159 | To check if the user is able to create a merchant with the following details. Merchant ID : M1 Description : Only Mada Credit Profile : Mada, GCC Debit Profile : Mada, GCC Commission Type : Percentage mada 0.08% VC/MV 3% CAP : 0 (unlimited) Setup : Setup 250 Recurring : XX Inactive : 100 Comments : 'Process payments for enabled and disabled services Upload Stocks : Upload 100 POS Assign Stocks : assign 1 POS (Note : -Check POS status -Check POS history -Check reports -Check TID format (16 digit new format) -Reassignment should be applied only to status=Pulled Out -Transactions to cancelled POS should be rejected) Merchant Info : Segment A Account info : Assign credit and debit accounts Address :XXX Contact : Mobile Email Card Product : Enable services as per the commission Account : Different accounts per card product (schemes), account type and for SAR. |  |  |  | Merchant is created successfully as per the specification. -If the service is enabled: Transactions Payments are processed successfully with correct split between merchant and BSF. -If the service is disabled: Transactions should be rejected by AM. -Fees are processed successfully with the right events and GL. -VAT calculation. -Profitability is reflected in P&L system. -Valid that is features are not enabled, then AM should not process transactions, i.e. disabled VC, MC, key entry, refund G2-If case email is provided for MID, then the system to send statements for all acquiring transactions to that MID (POS, ePay, QR ...) in CSV format. -Accounts should be valid (existing and active accounts) |  |  | Business - BSF |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
160 | UAT - Apex | Apex Execution R1 | Merchant Onboarding |  |  |  | SCN-062 | To check if the user is able to create a merchant with only access to Credit cards |  | TC-160 | To check if the user is able to create a merchant with the following details. Merchant ID : M2 Description : Credit cards Credit Profile : VC, MC Debit Profile : Mada, GCC Commission Type : Percentage mada 0.07% VC/MV 2.5% CAP : mada 150,GCC 80 Fee commissions : Setup : Setup 250 Recurring : 250 per M Inactive : 50 Comments : 'Process payments for enabled and disabled services Upload Stocks : Upload 1500 POS Assign Stocks : assign 5 POS (Note : -Check POS status -Check POS history -Check reports -Check TID format (16 digit new format) -Reassignment should be applied only to status=Pulled Out -Transactions to cancelled POS should be rejected) Merchant Info : Segment non-A Account info : Assign credit and debit accounts Address :XXX Contact : XXX Card Product : Enable services as per the commission Account : Different accounts per card product (schemes), account type and for SAR. |  |  |  | Merchant is created successfully as per the specification. -If the service is enabled: Transactions Payments are processed successfully with correct split between merchant and BSF. -If the service is disabled: Transactions should be rejected by AM. -Fees are processed successfully with the right events and GL. -VAT calculation. -Profitability is reflected in P&L system. -Valid that is features are not enabled, then AM should not process transactions, i.e. disabled VC, MC, key entry, refund G2-If case email is provided for MID, then the system to send statements for all acquiring transactions to that MID (POS, ePay, QR ...) in CSV format. -Accounts should be valid (existing and active accounts) |  |  | Business - BSF |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
161 | UAT - Apex | Apex Execution R1 | Merchant Onboarding |  |  |  | SCN-063 | To check if the user is able to create a merchant with only access to Amex |  | TC-161 | To check if the user is able to create a merchant with the following details. Merchant ID : M3 Description : Amex Credit Profile : VC, MC,Amex Debit Profile : Mada, GCC Commission Type : Percentage mada 0.6%% VC/MV 2% CAP : mada 40,GCC 80 Fee commissions : Setup : Maintenance 200 Recurring : 250 per M Inactive : 50 Comments : 'Process payments for enabled and disabled services Upload Stocks : Upload 100 POS Assign Stocks : assign 10 POS (Note : -Check POS status -Check POS history -Check reports -Check TID format (16 digit new format) -Reassignment should be applied only to status=Pulled Out -Transactions to cancelled POS should be rejected) Merchant Info : Segment non-A Account info : Assign credit and debit accounts Address :XXX Contact : XXX Card Product : Enable services as per the commission Account : Different accounts per card product (schemes), account type and for SAR. |  |  |  | Merchant is created successfully as per the specification. -If the service is enabled: Transactions Payments are processed successfully with correct split between merchant and BSF. -If the service is disabled: Transactions should be rejected by AM. -Fees are processed successfully with the right events and GL. -VAT calculation. -Profitability is reflected in P&L system. -Valid that is features are not enabled, then AM should not process transactions, i.e. disabled VC, MC, key entry, refund G2-If case email is provided for MID, then the system to send statements for all acquiring transactions to that MID (POS, ePay, QR ...) in CSV format. -Accounts should be valid (existing and active accounts) |  |  | Business - BSF |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
162 | UAT - Apex | Apex Execution R1 | Merchant Onboarding |  |  |  | SCN-064 | To check if the user is able to create a merchant with only access to Discover |  | TC-162 | To check if the user is able to create a merchant with the following details. Merchant ID : M4 Description : Discover Credit Profile : VC, MC,Discover Debit Profile : Mada, GCC Commission Type : Percentage mada 0.05% VC/MV 1.75% CAP : mada 160,GCC 80 Fee commissions : Setup : 0 Recurring : 400 per Y Inactive : 0 Comments : 'Process payments for enabled and disabled services Upload Stocks : 0 Assign Stocks : 0 (Note : -Check POS status -Check POS history -Check reports -Check TID format (16 digit new format) -Reassignment should be applied only to status=Pulled Out -Transactions to cancelled POS should be rejected) Merchant Info : XXX Account info : Assign credit and debit accounts Address :XXX Contact : XXX Card Product : Enable services as per the commission Account : Different accounts per card product (schemes), account type and for SAR. |  |  |  | Merchant is created successfully as per the specification. -If the service is enabled: Transactions Payments are processed successfully with correct split between merchant and BSF. -If the service is disabled: Transactions should be rejected by AM. -Fees are processed successfully with the right events and GL. -VAT calculation. -Profitability is reflected in P&L system. -Valid that is features are not enabled, then AM should not process transactions, i.e. disabled VC, MC, key entry, refund G2-If case email is provided for MID, then the system to send statements for all acquiring transactions to that MID (POS, ePay, QR ...) in CSV format. -Accounts should be valid (existing and active accounts) |  |  | Business - BSF |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
163 | UAT - Apex | Apex Execution R1 | Merchant Onboarding |  |  |  | SCN-065 | To check if the user is able to create a merchant with only access to Discover and Amex |  | TC-163 | To check if the user is able to create a merchant with the following details. Merchant ID : M5 Description : Discover and Amex Credit Profile : VC, MC,Discover,Amex Debit Profile : Mada, GCC Commission Type : Percentage mada 0.04% VC/MV 1.5% CAP : mada 160,GCC 80 Fee commissions : Setup : 0 Recurring : 10 per W Inactive : 0 Comments : 'Process payments for enabled and disabled services Upload Stocks : 0 Assign Stocks : 0 (Note : -Check POS status -Check POS history -Check reports -Check TID format (16 digit new format) -Reassignment should be applied only to status=Pulled Out -Transactions to cancelled POS should be rejected) Merchant Info : XXX Account info : Assign credit and debit accounts Address :XXX Contact : XXX Card Product : Enable services as per the commission Account : Different accounts per card product (schemes), account type and for SAR. |  |  |  | Merchant is created successfully as per the specification. -If the service is enabled: Transactions Payments are processed successfully with correct split between merchant and BSF. -If the service is disabled: Transactions should be rejected by AM. -Fees are processed successfully with the right events and GL. -VAT calculation. -Profitability is reflected in P&L system. -Valid that is features are not enabled, then AM should not process transactions, i.e. disabled VC, MC, key entry, refund G2-If case email is provided for MID, then the system to send statements for all acquiring transactions to that MID (POS, ePay, QR ...) in CSV format. -Accounts should be valid (existing and active accounts) |  |  | Business - BSF |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
164 | UAT - Apex | Apex Execution R1 | Merchant Onboarding | [6 empty] | TC-164 | To check whether user is able to process valid authorization and capturing |  |  |  | '-Try on mada, VC, MC, Discover and Amex -Upon processing the transaction, AM should receive authorization, and should be stored in the system. -Next, upon processing capturing, AM should validate that the authorization belong to the same merchant, and the amount is equal or less that the authorized amount. |  |  | Business - BSF |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
165 | UAT - Apex | Apex Execution R1 | Merchant Onboarding | [6 empty] | TC-165 | To check whether user is able to process only capturing |  |  |  | 'Upon processing capturing, AM will not match the entered authorization number, then this should be rejected. |  |  | Business - BSF |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
166 | UAT - Apex | Apex Execution R1 | Merchant Onboarding | [6 empty] | TC-166 | To check whether user is able to amount is higher then authorized |  |  |  | 'Upon processing capturing, AM will match the entered authorization number but the amount is higher than the authorized amount, then this should be rejected. |  |  | Business - BSF |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
167 | UAT - Apex | Apex Execution R1 | Merchant Onboarding | [6 empty] | TC-167 | To check whether user is able to Refund transaction |  |  |  | -Try on mada, VC, MC, Discover and Amex -Process normal transaction -Process a refund transaction. -Validate that the original transaction exists and the amount is equal or less. -Process refunding (successful) |  |  | Business - BSF |  |  | 2021-11-30 | 2021-11-30 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 2 | 100% | 0% | Pending | W15
168 | UAT - Apex | Apex Execution R1 | Merchant Onboarding | [6 empty] | TC-168 | To check whether user is able to Refund for invalid transaction |  |  |  | -Process a refund transaction. -Since there is no original transaction, refund should be rejected |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
169 | UAT - Apex | Apex Execution R1 | Merchant Onboarding | [6 empty] | TC-169 | To check whether user is able to Refund amount is higher than the original |  |  |  | -Process a refund transaction with higher amount. -Since the refunded amount is greater than the original transaction, refund should be rejected. |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
170 | UAT - Apex | Apex Execution R1 | Merchant Onboarding |  |  |  | SCN-066 | To check if the user is able to create a merchant with only access to Hala (Single MID) |  | TC-170 | To check if the user is able to create a merchant with the following details. Merchant ID : M6 Description : Hala (Single MID) Credit Profile : VC, MC. Debit Profile : Mada, GCC Commission Type : Percentage mada 0.07% VC/MV 3% CAP : mada 160,GCC 80 Fee commissions : Setup : 0 Recurring : 5 per D Inactive : 0 Comments : 'Process payments for enabled and disabled services Upload Stocks : 0 Assign Stocks : Assign 200 POS (Note : -Check POS status -Check POS history -Check reports -Check TID format (16 digit new format) -Reassignment should be applied only to status=Pulled Out -Transactions to cancelled POS should be rejected) Merchant Info : XXX Account info : Assign credit and debit accounts Address :XXX Contact : XXX Card Product : Enable services as per the commission Account : Different accounts per card product (schemes), account type and for SAR. |  |  |  | Merchant is created successfully as per the specification. -If the service is enabled: Transactions Payments are processed successfully with correct split between merchant and BSF. -If the service is disabled: Transactions should be rejected by AM. -Fees are processed successfully with the right events and GL. -VAT calculation. -Profitability is reflected in P&L system. -Valid that is features are not enabled, then AM should not process transactions, i.e. disabled VC, MC, key entry, refund G2-If case email is provided for MID, then the system to send statements for all acquiring transactions to that MID (POS, ePay, QR ...) in CSV format. -Accounts should be valid (existing and active accounts) |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
171 | UAT - Apex | Apex Execution R1 | Merchant Onboarding |  |  |  | SCN-067 | To check if the user is able to create a merchant with only access to Hala (Single MID) |  | TC-171 | To check if the user is able to create a merchant with the following details. Merchant ID : M7 Description : Hala (multi MID) Credit Profile : VC, MC. Debit Profile : Mada, GCC Commission Type : Percentage mada 0.07% VC/MV 3% CAP : mada 160,GCC 80 Fee commissions : Setup : 0 Recurring : 0 Inactive : 0 Comments : 'Process payments for enabled and disabled services Upload Stocks : 0 Assign Stocks : 0 (Note : -Check POS status -Check POS history -Check reports -Check TID format (16 digit new format) -Reassignment should be applied only to status=Pulled Out -Transactions to cancelled POS should be rejected) Merchant Info : XXX Account info : Assign credit and debit accounts Address :XXX Contact : XXX Card Product : Enable services as per the commission Account : Different accounts per card product (schemes), account type and for SAR. |  |  |  | Merchant is created successfully as per the specification. -If the service is enabled: Transactions Payments are processed successfully with correct split between merchant and BSF. -If the service is disabled: Transactions should be rejected by AM. -Fees are processed successfully with the right events and GL. -VAT calculation. -Profitability is reflected in P&L system. -Valid that is features are not enabled, then AM should not process transactions, i.e. disabled VC, MC, key entry, refund G2-If case email is provided for MID, then the system to send statements for all acquiring transactions to that MID (POS, ePay, QR ...) in CSV format. -Accounts should be valid (existing and active accounts) |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
172 | UAT - Apex | Apex Execution R1 | Merchant Onboarding |  |  |  | SCN-068 | To check if the user is able to create a merchant with only access to Soft POS |  | TC-172 | To check if the user is able to create a merchant with the following details. Merchant ID : M8 Description : Soft POS Credit Profile : VC, MC. Debit Profile : Mada, GCC Commission Type : Percentage mada 0.07% VC/MV 3% CAP : mada 160,GCC 80 Fee commissions : Setup : 0 Recurring : 0 Inactive : 0 Comments : 'Process payments for enabled and disabled services Upload Stocks : Upload Soft POS 100 Assign Stocks : Assign 100 POS (Note : -Check POS status -Check POS history -Check reports -Check TID format (16 digit new format) -Reassignment should be applied only to status=Pulled Out -Transactions to cancelled POS should be rejected) Merchant Info : XXX Account info : Assign credit and debit accounts Address :XXX Contact : XXX Card Product : Enable services as per the commission Account : Different accounts per card product (schemes), account type and for SAR. |  |  |  | Merchant is created successfully as per the specification. -If the service is enabled: Transactions Payments are processed successfully with correct split between merchant and BSF. -If the service is disabled: Transactions should be rejected by AM. -Fees are processed successfully with the right events and GL. -VAT calculation. -Profitability is reflected in P&L system. -Valid that is features are not enabled, then AM should not process transactions, i.e. disabled VC, MC, key entry, refund G2-If case email is provided for MID, then the system to send statements for all acquiring transactions to that MID (POS, ePay, QR ...) in CSV format. -Accounts should be valid (existing and active accounts) |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
173 | UAT - Apex | Apex Execution R1 | Merchant Onboarding |  |  |  | SCN-069 | To check if the user is able to create a merchant with only access to Only mada debit |  | TC-173 | To check if the user is able to create a merchant with the following details. Merchant ID : M9 Description : Only mada debit Credit Profile : N/A. Debit Profile : Mada, GCC Commission Type : Flat 0.08 SAR CAP : mada 160 Fee commissions : Setup : 0 Recurring : 0 Inactive : 0 Comments : 'Process payments for enabled and disabled services Upload Stocks : 0 Assign Stocks : 0 (Note : -Check POS status -Check POS history -Check reports -Check TID format (16 digit new format) -Reassignment should be applied only to status=Pulled Out -Transactions to cancelled POS should be rejected) Merchant Info : XXX Account info : Assign credit and debit accounts Address :XXX Contact : XXX Card Product : Enable services as per the commission Account : Different accounts per card product (schemes), account type and for SAR. |  |  |  | Merchant is created successfully as per the specification. -If the service is enabled: Transactions Payments are processed successfully with correct split between merchant and BSF. -If the service is disabled: Transactions should be rejected by AM. -Fees are processed successfully with the right events and GL. -VAT calculation. -Profitability is reflected in P&L system. -Valid that is features are not enabled, then AM should not process transactions, i.e. disabled VC, MC, key entry, refund G2-If case email is provided for MID, then the system to send statements for all acquiring transactions to that MID (POS, ePay, QR ...) in CSV format. -Accounts should be valid (existing and active accounts) |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
174 | UAT - Apex | Apex Execution R1 | Merchant Onboarding | [6 empty] | TC-174 | To check if the user is able to create a merchant with the following details. Merchant ID : M10 Description : Only mada debit Credit Profile : N/A. Debit Profile : Mada, GCC Commission Type : Scale mada < 100 then 0.07 => 100 then 0.08 CAP : mada 160 Fee commissions : Setup : 0 Recurring : 0 Inactive : 0 Comments : 'Process payments for enabled and disabled services Upload Stocks : 0 Assign Stocks : 0 (Note : -Check POS status -Check POS history -Check reports -Check TID format (16 digit new format) -Reassignment should be applied only to status=Pulled Out -Transactions to cancelled POS should be rejected) Merchant Info : XXX Account info : Assign credit and debit accounts Address :XXX Contact : XXX Card Product : Enable services as per the commission Account : Different accounts per card product (schemes), account type and for SAR. |  |  |  | Merchant is created successfully as per the specification. -If the service is enabled: Transactions Payments are processed successfully with correct split between merchant and BSF. -If the service is disabled: Transactions should be rejected by AM. -Fees are processed successfully with the right events and GL. -VAT calculation. -Profitability is reflected in P&L system. -Valid that is features are not enabled, then AM should not process transactions, i.e. disabled VC, MC, key entry, refund G2-If case email is provided for MID, then the system to send statements for all acquiring transactions to that MID (POS, ePay, QR ...) in CSV format. -Accounts should be valid (existing and active accounts) |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
175 | UAT - Apex | Apex Execution R1 | Merchant Onboarding |  |  |  | SCN-070 | To check if the user is able to create a merchant with only access to Only ePay |  | TC-175 | To check if the user is able to create a merchant with the following details. Merchant ID : M11 Description : ePay Credit Profile : VC/MC. Debit Profile : Mada, GCC Commission Type : Flat + Percentage mada 1.75% VC/MC 3.5% + 1 SAR CAP : N/A Fee commissions : Setup : 0 Recurring : 0 Inactive : 0 Comments : 'Process payments for enabled and disabled services Upload Stocks : 0 Assign Stocks : Assign 1 VPOS (Note : -Check POS status -Check POS history -Check reports -Check TID format (16 digit new format) -Reassignment should be applied only to status=Pulled Out -Transactions to cancelled POS should be rejected) Merchant Info : XXX Account info : Assign credit and debit accounts Address :XXX Contact : XXX Card Product : Enable services as per the commission Account : Different accounts per card product (schemes), account type and for SAR. |  |  |  | Merchant is created successfully as per the specification. -If the service is enabled: Transactions Payments are processed successfully with correct split between merchant and BSF. -If the service is disabled: Transactions should be rejected by AM. -Fees are processed successfully with the right events and GL. -VAT calculation. -Profitability is reflected in P&L system. -Valid that is features are not enabled, then AM should not process transactions, i.e. disabled VC, MC, key entry, refund G2-If case email is provided for MID, then the system to send statements for all acquiring transactions to that MID (POS, ePay, QR ...) in CSV format. -Accounts should be valid (existing and active accounts) |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
176 | UAT - Apex | Apex Execution R1 | Merchant Onboarding |  |  |  | SCN-071 | To check if the user is able to create a merchant with only access to Only QR |  | TC-176 | To check if the user is able to create a merchant with the following details. Merchant ID : M12 Description : QR Credit Profile : N/A. Debit Profile : Mada, GCC Commission Type : to be defined as per new SAMA charge scheme CAP : 0 Fee commissions : Setup : 0 Recurring : 0 Inactive : 0 Comments : 'Process payments for enabled and disabled services Upload Stocks : 0 Assign Stocks : Assign 1 VPOS (Note : -Check POS status -Check POS history -Check reports -Check TID format (16 digit new format) -Reassignment should be applied only to status=Pulled Out -Transactions to cancelled POS should be rejected) Merchant Info : XXX Account info : Assign credit and debit accounts Address :XXX Contact : XXX Card Product : Enable services as per the commission Account : Different accounts per card product (schemes), account type and for SAR. |  |  |  | Merchant is created successfully as per the specification. -If the service is enabled: Transactions Payments are processed successfully with correct split between merchant and BSF. -If the service is disabled: Transactions should be rejected by AM. -Fees are processed successfully with the right events and GL. -VAT calculation. -Profitability is reflected in P&L system. -Valid that is features are not enabled, then AM should not process transactions, i.e. disabled VC, MC, key entry, refund G2-If case email is provided for MID, then the system to send statements for all acquiring transactions to that MID (POS, ePay, QR ...) in CSV format. -Accounts should be valid (existing and active accounts) |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
177 | UAT - Apex | Apex Execution R1 | Merchant Onboarding |  |  |  | SCN-072 | To check if the user is able to create a merchant |  | TC-177 | To check if the user is able to create a merchant with the following details. Merchant ID : M13 Description : XX Credit Profile : N/A. Debit Profile : XX Commission Type : to be defined as per new SAMA charge scheme CAP : 0 Fee commissions : Setup : 0 Recurring : 0 Inactive : 0 Comments : 'Process payments for enabled and disabled services Upload Stocks : 0 Assign Stocks : 0 (Note : -Check POS status -Check POS history -Check reports -Check TID format (16 digit new format) -Reassignment should be applied only to status=Pulled Out -Transactions to cancelled POS should be rejected) Merchant Info : XXX Account info : Assign credit and debit accounts Address :XXX Contact : XXX Card Product : Enable services as per the commission Account : Different accounts per card product (schemes), account type and for SAR. |  |  |  | -since mada does not support key entry, then this should be rejected. |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
178 | UAT - Apex | Apex Execution R1 | Merchant Management | Merchant Maintenance-Business | Merchant Maintenance-Business | Merchant Request(Non financial modification) | SCN-073 | To check the user is able to modify the merchant details |  | TC-178 | To check the user is able to Enable CC |  |  |  | Enabling of CC has to be successful and Changes has to get reflected in the merchant profile |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
179 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-179 | To check the user is able to Disable CC |  |  |  | Disabling of CC has to be successful and Changes has to get reflected in the merchant profile |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
180 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-180 | To check the user is able to Enable Key entry |  |  |  | Enabling of Key entry has to be successful and Changes has to get reflected in the merchant profile |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
181 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-181 | To check the user is able to Disable Key entry |  |  |  | Disabling of Key entry has to be successful and Changes has to get reflected in the merchant profile |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
182 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-182 | To check the user is able to Enable Refund |  |  |  | Enabling of Refund has to be successful and Changes has to get reflected in the merchant profile |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
183 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-183 | To check the user is able to Disable Refund |  |  |  | Disabling of Refund has to be successful and Changes has to get reflected in the merchant profile |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
184 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-184 | To check the user is able to modify/update the Address |  |  |  | Updating of address has to be successful and Changes has to get reflected in the merchant profile |  |  | Business - BSF |  |  | 2021-12-01 | 2021-12-01 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 1 | 100% | 0% | Pending | W15
185 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-185 | To check the user is able to modify/update Contact number |  |  |  | Updating of contact number has to be successful and Changes has to get reflected in the merchant profile |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W15
186 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-186 | To check the user is able to modify/update Account number |  |  |  | Updating of Account number has to be successful and Changes has to get reflected in the merchant profile |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W15
187 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-187 | To check the user is able to modify/update Relocation in same region |  |  |  | New terminal ID should be created and assigned to new merchant |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W15
188 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-188 | To check the user is able to modify/update Relocation in different region |  |  |  | Creation of a new terminal ID should be created and assign to a new merchant |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W15
189 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  |  | SCN-074 | To check the user is able to cancel the terminals |  | TC-189 | To check the user is able to Cancel terminals |  |  |  | Change in the status, and after unlinked, terminal ID to be 8 rather than 16 digits |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W15
190 | UAT - Apex | Apex Execution R1 | Merchant Management | [6 empty] | TC-190 | To check the user is able to Pull out terminals |  |  |  | Change in the status, and after unlinked, terminal ID to be 8 rather than 16 digits |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W15
191 | UAT - Apex | Apex Execution R1 | Merchant Management |  |  |  | SCN-075 | To check the user is able to Replace the terminals |  | TC-191 | To check the user is able to Cancel terminals and replace for new terminals |  |  |  | Check status of cancelled and assigned terminals |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W15
192 | UAT - Apex | Apex Execution R1 | Reports | Reports | Reports | Reports | SCN-076 | To Validate Registration (new merchant) report with appropriate template with format |  | TC-192 | To check if the user is able to generate Registration (new merchant) report and to verify all the contents in the report |  |  |  | Report content and layout should be as per business expectation |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  | 2021-11-17 | FAIL |  | BAAP-23, BAAP-30 |  |  |  |  | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 100% | Pending | W15 | W23
193 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-077 | To Validate Replacement report with appropriate template with format |  | TC-193 | To check if the user is able to generate Replacement report and to verify all the contents in the report |  |  |  | Report content and layout should be as per business expectation |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W15
194 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-078 | To Validate reassign report with appropriate template with format |  | TC-194 | To check if the user is able to generate Reassign report and to verify all the contents in the report |  |  |  | Report content and layout should be as per business expectation |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W15
195 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-079 | To Validate Cancellation report with appropriate template with format |  | TC-195 | To check if the user is able to generate Cancellation report and to verify all the contents in the report |  |  |  | Report content and layout should be as per business expectation |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W15
196 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-080 | To Validate (MASS2) Retailer information and history report with appropriate template with format |  | TC-196 | To check if the user is able to generate (MASS2) Retailer information and history report and to verify all the contents in the report |  |  |  | Report content and layout should be as per business expectation |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W15
197 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-081 | To Validate Daily report for new terminals with appropriate template with format |  | TC-197 | To check if the user is able to generate Daily report for new terminals and to verify all the contents in the report |  |  |  | Report content and layout should be as per business expectation |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W15
198 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-082 | To Validate Soft POS report with appropriate template with format |  | TC-198 | To check if the user is able to generate Soft POS report and to verify all the contents in the report |  |  |  | Report content and layout should be as per business expectation |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W15
199 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-083 | To Validate Daily updated Commissions report with appropriate template with format |  | TC-199 | To check if the user is able to generate Daily updated Commissions report and to verify all the contents in the report |  |  |  | Report content and layout should be as per business expectation |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W15
200 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-084 | To Validate Daily Commission History (Audit Trail) report with appropriate template with format |  | TC-200 | To check if the user is able to generate Commission History (Audit Trail) report and to verify all the contents in the report |  |  |  | Report content and layout should be as per business expectation |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W15
201 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-085 | To Validate Merchant Details with commissions report with appropriate template with format |  | TC-201 | To check if the user is able to generate Merchant Details with commissions report and to verify all the contents in the report |  |  |  | Report content and layout should be as per business expectation |  |  | Business - BSF |  |  | 2021-12-02 | 2021-12-02 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W15
202 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-086 | To Validate Terminals Details, i.e. TID, CPT, MID, Merchant name, Type (Physical, Soft, ePay, QR), scheme, Status, dates, location, and Transaction value and volume report with appropriate template with format |  | TC-202 | To check if the user is able to generate Terminals Details, i.e. TID, CPT, MID, Merchant name, Type (Physical, Soft, ePay, QR), scheme, Status, dates, location, and Transaction value and volume report and to verify all the contents in the report |  |  |  | Report content and layout should be as per business expectation |  |  | Business - BSF |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
203 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-087 | To Validate List of all key entry transactions report with appropriate template with format |  | TC-203 | To check if the user is able to generate List of all key entry transactions report and to verify all the contents in the report |  |  |  | Report content and layout should be as per business expectation |  |  | Business - BSF |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
204 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-088 | To Validate List of all refunded transactions report with appropriate template with format |  | TC-204 | To check if the user is able to generate List of all Refunded transactions report and to verify all the contents in the report |  |  |  | Report content and layout should be as per business expectation |  |  | Business - BSF |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
205 | UAT - Apex | Apex Execution R1 | Settlement Process | Settlement Process | Settlement Process | Clearing & Reconciliation | SCN-089 | To validate the files processing |  | TC-205 | Load Incoming MIGS Files |  |  |  | The transactions should properly be populated in TRANS_LOG, MIGS_HDR and MIGS_DTL tables |  |  | Business - BSF |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
206 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-206 | Load incoming EP747 file from VISA after uploading the file to VISA |  |  |  | IPM file generation should include the MasterCard transactions that were received in the incoming DCF file |  |  | Business - BSF |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
207 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-207 | Load TT068 MasterCard full replacement Bin file (received twice a year) |  |  |  | The corresponding IRD table should be filled |  |  | Business - BSF |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
208 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-208 | Load TT067 MasterCard BIN file |  |  |  | The corresponding IRD table should be updated |  |  | Business - BSF |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
209 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-209 | Load incoming TT113 file from MC after uploading the file to MasterCard |  |  |  | The summary should be reflected in MCSETRECON and in case of rejections MCSETREJLOG should be filled |  |  | Business - BSF |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
210 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-210 | Generate outgoing BASE II file |  |  |  | The file should include all the POS and ECOM VISA (local credit and all international) transactions make sure refund and purchase are properly reflected |  |  | Business - BSF |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
211 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-211 | Generate outgoing IPM file |  |  |  | The file should include all the POS and ECOM MC (local credit and all international) transactions and purchase are properly reflected |  |  | Business - BSF |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
212 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-212 | Generate outgoing Discover file |  |  |  | File format should match the new format by the scheme. |  |  | Business - BSF |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
213 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-213 | Run Merchant Processor |  |  |  | Payments should be generated properly by scheme VISA, MC, mada, GCC, UPI |  |  | Business - Maveric |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
214 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-214 | Load Response file |  |  |  | Response file should be successful loaded and should reflect the processed payments to merchants |  |  | Business - Maveric |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
215 | UAT - Apex | Apex Execution R1 | Settlement Process |  |  | Settlement Process Module | SCN-090 | To validate the On-Us POS Transaction posting Visa/MC |  | TC-215 | To validate Posting On-Us Visa sales transaction |  |  |  | Simulated On-Us Visa sales draft POS Transaction should be posted with the channel as Onus "Channel On-Us" in the Acquirer Application All the details should be appropriate in the transaction detail screen |  |  | Business - Maveric |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
216 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-216 | To validate Posting On-Us MC sales transaction |  |  |  | Simulated On-Us MC sales draft POS Transaction should be posted with the channel as Onus "Channel On-Us" in the Acquirer Application All the details should be appropriate in the transaction detail screen |  |  | Business - Maveric |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
217 | UAT - Apex | Apex Execution R1 | Settlement Process |  |  |  | SCN-091 | To validate the Off-Us POS Transaction posting Visa/MC |  | TC-217 | To validate Posting OFFUS Visa sales transaction |  |  |  | Simulated OFFUS Visa sales draft POS Transaction should be posted with the channel as Onus "Channel OFFUS" in the Acquirer Application All the details should be appropriate in the transaction detail screen |  |  | Business - Maveric |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
218 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-218 | To validate Posting OFFUS MC sales transaction |  |  |  | Simulated OFFUS MC sales draft POS Transaction should be posted with the channel as Onus "Channel OFFUS" in the Acquirer Application All the details should be appropriate in the transaction detail screen |  |  | Business - Maveric |  |  | 2021-12-05 | 2021-12-05 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
219 | UAT - Apex | Apex Execution R1 | Settlement Process |  |  |  | SCN-092 | To validate the On-Us ATM Transaction posting Visa/MC |  | TC-219 | To validate Posting On-Us Visa ATM Withdrawal transaction |  |  |  | Simulated On-Us Visa ATM draft POS Transaction should be posted with the channel as Onus "Channel On-Us" in the Acquirer Application All the details should be appropriate in the transaction detail screen |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
220 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-220 | To validate Posting On-Us MC ATM Withdrawal transaction |  |  |  | Simulated On-Us MC ATM draft POS Transaction should be posted with the channel as Onus "Channel On-Us" in the Acquirer Application All the details should be appropriate in the transaction detail screen |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
221 | UAT - Apex | Apex Execution R1 | Settlement Process |  |  |  | SCN-093 | To validate the Off-Us ATM Transaction posting Visa/MC |  | TC-221 | To validate Posting Off-Us Visa ATM Withdrawal transaction |  |  |  | Simulated OFFUS Visa ATM draft POS Transaction should be posted with the channel as Onus "Channel OFFUS" in the Acquirer Application All the details should be appropriate in the transaction detail screen |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
222 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-222 | To validate Posting Off-Us MC ATM Withdrawal transaction |  |  |  | Simulated OFFUS MC ATM draft POS Transaction should be posted with the channel as Onus "Channel OFFUS" in the Acquirer Application All the details should be appropriate in the transaction detail screen |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
223 | UAT - Apex | Apex Execution R1 | Settlement Process |  |  |  | SCN-094 | To validate the On-Us e-commerce Transaction posting Visa/MC |  | TC-223 | To validate Posting Visa e-commerce transaction |  |  |  | Simulated Visa Transaction should be posted in the Acquirer Application All the details should be appropriate in the transaction detail screen |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
224 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-224 | To validate Posting On-Us MC e-commerce transaction |  |  |  | Simulated MC Transaction should be posted in the Acquirer Application All the details should be appropriate in the transaction detail screen |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
225 | UAT - Apex | Apex Execution R1 | Settlement Process |  |  | Daily Pay-outs | SCN-095 | To validate payments to Merchants |  | TC-225 | Validate the Daily Pay-outs file to Merchants |  |  |  | The payments should get transferred to the merchant account successfully |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
226 | UAT - Apex | Apex Execution R1 | Fees | Fees | Fees | Entry Rates Overriding | SCN-096 | To validate Override user entry rates |  | TC-226 | To validate if overriding the user entry rates is possible |  |  |  | Overriding should be successful for the rate implemented by the user |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W16
227 | UAT - Apex | Apex Execution R1 | Fees |  |  | POS Fees | SCN-097 | To validate POS Fee deduction based on the various criteria |  | TC-227 | To validate POS Fees for inactive terminal |  |  |  | Charges should be applied successfully of 100SR |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W16
228 | UAT - Apex | Apex Execution R1 | Fees |  |  | e-commerce (ePay) fees | SCN-098 | To validate e-commerce Fee deduction |  | TC-228 | Setup fee (one time fee) |  |  |  | Monthly Services setup fee should be deducted successfully from Merchant to BSF |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W16
229 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-229 | Fraud Fee (one time fee) |  |  |  | Monthly Fraud Fee should be deducted successfully from Merchant to BSF |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W16
230 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-230 | Monthly fee (Fixed amount deducted per month) |  |  |  | Monthly Fees should be deducted successfully from Merchant to BSF |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W16
231 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-231 | User Fee (Fixed amount per user deducted monthly) - Number of Users: when not empty/blank, User fee will be charged. |  |  |  | Monthly User Fee should be deducted successfully from Merchant to BSF |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W16
232 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-232 | User Fee (Fixed amount per user deducted monthly) - Number of Users: when empty/blank, User fee will not be charged. |  |  |  | Monthly User Fee should not be deducted from Merchant to BSF if no.of user is empty/blank |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W16
233 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-233 | Discount Rate: (Flat fixed amount + Percentage from total amount with no limit) - VISA |  |  |  | Discount Rate should be applied (Flat fixed amount + Percentage from total amount with no limit for e-comm successfully |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W16
234 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-234 | Discount Rate: (Flat fixed amount + Percentage from total amount with no limit) - MC |  |  |  | Discount Rate should be applied (Flat fixed amount + Percentage from total amount with no limit for e-comm successfully |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W16
235 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-235 | MADA Interchange Fees |  |  |  | Calculated 0.70% from transaction value paid by the acquiring bank to the issuing bank should be successful |  |  | Business - Maveric |  |  | 2021-12-06 | 2021-12-06 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W16
236 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-236 | Refund Fee: fixed amount per transaction |  |  |  | Monthly Refund Fee should be deducted successfully from Merchant to BSF |  |  | Business - Maveric |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W16
237 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-237 | Chargeback fee: fixed amount per transaction |  |  |  | Monthly Charge back Fee should be deducted successfully from Merchant to BSF |  |  | Business - Maveric |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W16
238 | UAT - Apex | Apex Execution R1 | Fees | [6 empty] | TC-238 | Failed transaction fee: fixed amount per transaction |  |  |  | Monthly Failed transaction Fee should be deducted successfully from Merchant to BSF |  |  | Business - Maveric |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan/Omer | BSF IT | Awaiting basic configuration defect fix- Awaiting data from BSF Business | 1 | 0 | 0% | 0% | Pending | W16
239 | UAT - Apex | Apex Execution R1 | Reports | Reports | Reports | Settlement and Reconciliation | SCN-099 | To Validate wings clearing report with appropriate template with format |  | TC-239 | To check if the user is able to generate wings clearing report and to verify and reconcile the events related to credit card clearing settlements |  |  |  | All Field level should be displayed by the system as per the expectation and events related to credit card clearing settlements should be available |  |  | Business - BSF |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
240 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-100 | To Validate INET MasterCard report with appropriate template with format |  | TC-240 | To check if the user is able to generate INET MasterCard reports and to verify and reconcile the receipt of settlement from MasterCard |  |  |  | All Field level should be displayed by the system as per the expectation |  |  | Business - BSF |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
241 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-101 | To Validate outgoing transaction journal |  | TC-241 | To check if the user is able to generate Outgoing transaction journal and verify and reconcile the volumes of VISA and MC acquiring transactions |  |  |  | All Field level should be displayed by the system as per the expectation |  |  | Business - Maveric |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
242 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-102 | To validate MasterCard rejection report with appropriate template with format |  | TC-242 | To check if the user is able to generate MasterCard rejection report and to verify the transactions rejected by MasterCard |  |  |  | All Field level should be displayed by the system as per the expectation and the transactions rejected by MasterCard |  |  | Business - BSF |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
243 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-103 | To validate Visa Rejection report with appropriate template with format |  | TC-243 | To check if the user is able to generate Visa card rejection report and to verify the transactions rejected by Visa card |  |  |  | All Field level should be displayed by the system as per the expectation and the transactions rejected by Visa card |  |  | Business - BSF |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
244 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-104 | To validate suspense report with appropriate template with format |  | TC-244 | To check if the user is able to generate suspense report and to verify the rejections related to clearing account |  |  |  | All Field level should be displayed by the system as per the expectation |  |  | Business - BSF |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
245 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-105 | To validate VISA quarterly report with appropriate template with format |  | TC-245 | To check if the user is able to generate VISA quarterly report and to verify the format and information as per VISA requirement |  |  |  | All Field level should be displayed by the system as per the VISA requirement |  |  | Business - BSF |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
246 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-106 | To validate MasterCard quarterly report with appropriate template with format |  | TC-246 | To check if the user is able to generate MasterCard quarterly report and to verify the format and information as per MC requirement |  |  |  | All Field level should be displayed by the system as per the MC requirement |  |  | Business - BSF |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
247 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-107 | To validate VISA POS Acquirer rejection report with appropriate template with format |  | TC-247 | To check if the user is able to generate VISA POS Acquire rejection report and to verify the transactions rejected by VISA |  |  |  | All Field level should be displayed by the system as per the MC requirement |  |  | Business - Maveric |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
248 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-108 | To validate Miscellaneous Report with appropriate template with format |  | TC-248 | To check if the user is able to generate Miscellaneous report and to verify the format and information as per requirement |  |  |  | All Field level should be displayed by the system as per the requirement |  |  | Business - BSF |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
249 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-109 | To validate Outstanding Report (OGL, TLF) with appropriate template with format |  | TC-249 | To check if the user is able to generate Outstanding Report (OGL, TLF) and to verify the format and information as per requirement |  |  |  | All Field level should be displayed by the system as per the requirement |  |  | Business - BSF |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
250 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-110 | To validate POS Statements with appropriate template with format |  | TC-250 | To check if the user is able to generate POS Statements and to verify the format and information as per requirement |  |  |  | All Field level should be displayed by the system as per the requirement |  |  | Business - BSF |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
251 | UAT - Apex | Apex Execution R1 | Reports |  |  |  | SCN-111 | To validate Charge Back report with appropriate template with format |  | TC-251 | To check if the user is able to generate Charge Back report and to verify the format and information as per requirement |  |  |  | All Field level should be displayed by the system as per the requirement |  |  | Business - BSF |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
252 | UAT - Apex | Apex Execution R1 | Settlement Process | Settlement Process - Business | Settlement Process - Business | Clearing & Reconciliation | SCN-112 | To validate the files processing |  | TC-252 | Load incoming TLF01 (ATM ACQ) file |  |  |  | -Successful files loading into AC. -Validate mismatched transactions in the reports. |  |  | Business - BSF |  |  | 2021-12-07 | 2021-12-07 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
253 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-253 | Load incoming TLF02 (ATM ISS) file |  |  |  | -Successful files loading into AC. -Validate mismatched transactions in the reports. |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
254 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-254 | Load incoming TLF03 (POS ACQ) file |  |  |  | -Successful files loading into AC. -Validate mismatched transactions in the reports. |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
255 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-255 | Load incoming TLF04 (POS ISS) file |  |  |  | -Successful files loading into AC. -Validate mismatched transactions in the reports. |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
256 | UAT - Apex | Apex Execution R1 | Settlement Process | [6 empty] | TC-256 | Load incoming TLF05 (ePay ACQ) file |  |  |  | -Successful files loading into AC. -Validate mismatched transactions in the reports. |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
257 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-257 | Load incoming TLF06 (ePay ISS) file |  |  |  | -Successful files loading into AC. -Validate mismatched transactions in the reports. |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
258 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-258 | Load incoming TLF07 (later QR ACQ) file |  |  |  | -Successful files loading into AC. -Validate mismatched transactions in the reports. |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
259 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-259 | Load incoming TLF08 (later for QR ISS) file |  |  |  | -Successful files loading into AC. -Validate mismatched transactions in the reports. |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
260 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-260 | Generate and validate GL Posting file |  |  |  | File should be generated and posted in FAH successfully. '-Correct WINGS files format and content. -Successful posting to GL. -OGL file to be generated and loaded in AC successfully (transactions should be marked as succeeded or rejected) |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
261 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-261 | To validate incoming Visa rejection file |  |  |  | File should be loaded successfully |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
262 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-262 | To validate incoming MasterCard rejection file |  |  |  | File should be loaded successfully |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
263 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-263 | To validate incoming Discover file |  |  |  | File should be loaded successfully |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
264 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-264 | Load Claims file (CPS) |  |  |  | -Successful loading into AC. -Claims are displayed in AC -Valid for; --Type of transactions --Schemes; mada, VC, VM, Discover, QR --Acquiring transactions; POS, SoftPOS, ePay, QR, (ATM with RBG) |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
265 | UAT - Apex | Apex Execution R2 | Settlement Process |  |  |  | SCN-113 | Reconcile transactions between TFL files and GL response (OGL) |  | TC-265 | Reconcile TLF1 and OGL |  |  |  | Generation of reports should be successful for reconciliation |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
266 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-266 | Reconcile TLF2 and OGL |  |  |  | Generation of reports should be successful for reconciliation |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
267 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-267 | Reconcile TLF3 and OGL |  |  |  | Generation of reports should be successful for reconciliation |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
268 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-268 | Reconcile TLF4 and OGL |  |  |  | Generation of reports should be successful for reconciliation |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
269 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-269 | Reconcile TLF5 and OGL |  |  |  | Generation of reports should be successful for reconciliation |  |  | Business - BSF |  |  | 2021-12-08 | 2021-12-08 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
270 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-270 | Reconcile TLF6 and OGL |  |  |  | Generation of reports should be successful for reconciliation |  |  | Business - BSF |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
271 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-271 | Reconcile TLF7 and OGL |  |  |  | Generation of reports should be successful for reconciliation |  |  | Business - BSF |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
272 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-272 | Reconcile TLF8 and OGL |  |  |  | Generation of reports should be successful for reconciliation |  |  | Business - BSF |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
273 | UAT - Apex | Apex Execution R2 | Settlement Process |  |  |  | SCN-114 | Reconcile during charge back |  | TC-273 | Reconcile transactions between OGL and Charge Back account |  |  |  | Generation of reports should be successful for reconciliation |  |  | Business - BSF |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
274 | UAT - Apex | Apex Execution R2 | Settlement Process |  |  | Replications | SCN-115 | Replicate acquiring transactions from OPEN2 to Apex Clearing (AC) |  | TC-274 | Replicate different type of transactions and from different schemes (mada, VC, MC, Discover, QR) |  |  |  | Successful transactions replications from OPEN2 to AC in real time for; -Type of transactions -Schemes; mada, VC, VM, Discover, QR -Acquiring transactions; POS, SoftPOS, ePay, QR, (ATM with RBG) |  |  | Business - BSF |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
275 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-275 | To validate missing transactions in AC due to technical reasons |  |  |  | Transactions should be available in the Queue and to be processed later. No human intervention is required. Recommendation; add notification by AQC to monitor if queue volume is more than X. |  |  | Business - BSF |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
276 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-276 | To validate the manual creation of transaction if the missing transactions are not sent from SP to OPEN2 |  |  |  | Successful manual creation and posting in AC. |  |  | Business - BSF |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
277 | UAT - Apex | Apex Execution R2 | Settlement Process | [6 empty] | TC-277 | To validate the Duplicate transactions in OPEN2 |  |  |  | AC will load only one transaction and reject the duplicate's as there is a filtration in the replication process. |  |  | Business - BSF |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
278 | UAT - Apex | Apex Execution R2 | Settlement Process |  |  | Data | SCN-116 | To validate the transactions for last 180 days |  | TC-278 | To Validate the transactions are available in AC for 180 days for POS, SoftPOS, QR, ePay |  |  |  | AC should maintain Transactions for the last 180 days |  |  | Business - BSF |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
279 | UAT - Apex | Apex Execution R2 | Claim Management | Claim Management | Claim Management | Claim Management | SCN-117 | To validate charge back process via Visa online |  | TC-279 | To check if the amount is Debited from Visa online chargeback account and credited to clearing account systematically |  |  |  | The debit and credit entries should be captured |  |  | Business - Maveric |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
280 | UAT - Apex | Apex Execution R2 | Claim Management |  |  |  | SCN-118 | To validate charge back process via MasterCom |  | TC-280 | To check if the mandatory fields are captured correctly in the system |  |  |  | The below mandatory fields should be captured correctly. -ARN -Transaction currency -Settlement currency -Local currency |  |  | Business - Maveric |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
281 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-281 | To check if the transaction description is captured correctly in the system |  |  |  | The transaction description should be captured correctly as per requirement |  |  | Business - Maveric |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
282 | UAT - Apex | Apex Execution R2 | Claim Management |  |  | Interface files | SCN-119 | To validate the incoming exception files |  | TC-282 | To check the incoming VISA base II files and the exception transactions are matched |  |  |  | 1.APEX homepage should be displayed 2.User should be navigated to the screen to download the VISA Base II files 3. Visa Base II file should be generated successfully |  |  | Business - Maveric |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
283 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-283 | To check the incoming MasterCard IPM file and exception the transactions are Matched |  |  |  | 1.APEX homepage should be displayed 2.User should be navigated to the screen to download the MasterCard IPM file in APEX 3. MasterCard IPM file should be generated successfully |  |  | Business - Maveric |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
284 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-284 | To check the incoming VISA SMS files and the exception transactions are Matched |  |  |  | 1.APEX homepage should be displayed 2.User should be navigated to the screen to download the VISA SMS file in APEX 3. VISA SMS file should be generated successfully |  |  | Business - Maveric |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
285 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-285 | To check the incoming MasterCard MDS files and exception transactions are Matched |  |  |  | 1.APEX homepage should be displayed 2.User should be navigated to the screen to download the MasterCard MDS files in APEX 3.MasterCard MDS files should be generated successfully |  |  | Business - Maveric |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
286 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-286 | To check following information are all available in the CPS file, 1.Case number 2.Card number 3.Transaction Type, Amount, Date, Time 4.Network 5.Reason Code 6.Card Type 7.Creation date 8.Priority 9.Status 10.Action Taken 11.Completion date |  |  |  | The CPS file should contain all the related information. 1.Case number 2.Card number 3.Transaction Type, Amount, Date, Time 4.Network 5.ReasonCode 6.Card Type 7.Creation date 8.Priority 9.Status 10.Action Taken 11.Completion date |  |  | Business - Maveric |  |  | 2021-12-09 | 2021-12-09 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W16
287 | UAT - Apex | Apex Execution R2 | Claim Management |  | Claim Management - Business | Charge back | SCN-120 | Chargeback process - business |  | TC-287 | Inquiry for transaction to open a claim -search for mada onus to open merchant claim |  |  |  | Claim has to be opened successfully |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
288 | UAT - Apex | Apex Execution R2 | Claim Management |  |  |  | SCN-121 | To validate On-us purchase charge back on visa cards |  | TC-288 | To validate and manage the claim initiated by the cardholder |  |  |  | -Post the transaction to GL, and AC will close the claim directly. -If the posting was successful, then no further action in AC. -If the posting failed, rectify and re-post. -COG to provide the list of events |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
289 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-289 | To validate and manage the claim initiated by the merchant |  |  |  | -Post the transaction to GL, and AC will close the claim directly. -If the posting was successful, then no further action in AC. -If the posting failed, rectify and re-post. -COG to provide the list of events |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
290 | UAT - Apex | Apex Execution R2 | Claim Management |  |  |  | SCN-122 | To validate off-us purchase charge back on MADA card |  | TC-290 | To validate Off-us MADA charge back transaction via CPS |  |  |  | -Post the transaction to GL, and AC will close the claim directly. -If the posting was successful, then no further action in AC. -If the posting failed, rectify and re-post. -COG to provide the list of events |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
291 | UAT - Apex | Apex Execution R2 | Claim Management |  |  |  | SCN-123 | To validate International schemes for Charge Back |  | TC-291 | To validate the International Claims for Visa card |  |  |  | -Post the transaction to GL, and AC will close the claim directly. -If the posting was successful, then no further action in AC. -If the posting failed, rectify and re-post. -COG to provide the list of events |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
292 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-292 | To validate the International Claims for Master card |  |  |  | -Post the transaction to GL, and AC will close the claim directly. -If the posting was successful, then no further action in AC. -If the posting failed, rectify and re-post. -COG to provide the list of events |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
293 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-293 | To validate the International Claims for Discover card |  |  |  | -Post the transaction to GL, and AC will close the claim directly. -If the posting was successful, then no further action in AC. -If the posting failed, rectify and re-post. -COG to provide the list of events |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
294 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-294 | To validate the Incoming Charge back for Visa card |  |  |  | -Post the transaction to GL, and AC will close the claim directly. -If the posting was successful, then no further action in AC. -If the posting failed, rectify and re-post. -COG to provide the list of events |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
295 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-295 | To validate the Incoming Charge back for Master card |  |  |  | -Post the transaction to GL, and AC will close the claim directly. -If the posting was successful, then no further action in AC. -If the posting failed, rectify and re-post. -COG to provide the list of events |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
296 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-296 | To validate the Incoming Charge back for Discover card |  |  |  | -Post the transaction to GL, and AC will close the claim directly. -If the posting was successful, then no further action in AC. -If the posting failed, rectify and re-post. -COG to provide the list of events |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
297 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-297 | To validate the Rejection of Presentment from Visa |  |  |  | -Post the transaction to GL, and AC will close the claim directly. -If the posting was successful, then no further action in AC. -If the posting failed, rectify and re-post. -COG to provide the list of events |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
298 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-298 | To validate the Rejection of Presentment from Master |  |  |  | -Post the transaction to GL, and AC will close the claim directly. -If the posting was successful, then no further action in AC. -If the posting failed, rectify and re-post. -COG to provide the list of events |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
299 | UAT - Apex | Apex Execution R2 | Claim Management | [6 empty] | TC-299 | To validate the Rejection of Presentment from Discover |  |  |  | -Post the transaction to GL, and AC will close the claim directly. -If the posting was successful, then no further action in AC. -If the posting failed, rectify and re-post. -COG to provide the list of events |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
300 | UAT - Apex | Apex Execution R2 | Claim Management |  |  |  | SCN-124 | To validate the claim rejection for already raised claims |  | TC-300 | Raise a claim for a claim had been raised |  |  |  | Claim has to get rejected |  |  | Business - BSF |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
301 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting | Accounting entries & GL posting | Accounting entries & GL posting | PURCHASE REV INPUT ACQUIRER VISA DOMEST | SCN_125 | To validate accounting entries posting in FAH as per the provided account mapping document |  | TC-301 | To check if accounting entries and GL posting are appropriate for ADP1-PURCHASE REV INPUT ACQUIRER VISA DOMEST |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
302 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE INPUT ACQUIRER VISA DOMESTIC |  |  |  | TC-302 | To check if accounting entries and GL posting are appropriate for ADPP-PURCHASE INPUT ACQUIRER VISA DOMESTIC |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
303 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE REV INPUT ACQUIRER MAST INTL |  |  |  | TC-303 | To check if accounting entries and GL posting are appropriate for AIP1-PURCHASE REV INPUT ACQUIRER MAST INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-12 | 2021-12-12 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
304 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE INPUT ACQUIRER MASTER INTL |  |  |  | TC-304 | To check if accounting entries and GL posting are appropriate for AIPP-PURCHASE INPUT ACQUIRER MASTER INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
305 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE REV INPUT ACQUIRER MAST DOMEST |  |  |  | TC-305 | To check if accounting entries and GL posting are appropriate for AMP1-PURCHASE REV INPUT ACQUIRER MAST DOMEST |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
306 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE INPUT ACQUIRER MASTER DOMESTIC |  |  |  | TC-306 | To check if accounting entries and GL posting are appropriate for AMPP-PURCHASE INPUT ACQUIRER MASTER DOMESTIC |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
307 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE REV INPUT ACQUIRER VISA INTL |  |  |  | TC-307 | To check if accounting entries and GL posting are appropriate for AVP1-PURCHASE REV INPUT ACQUIRER VISA INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
308 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE INPUT ACQUIRER VISA INTL |  |  |  | TC-308 | To check if accounting entries and GL posting are appropriate for AVPP-PURCHASE INPUT ACQUIRER VISA INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
309 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE CHGBK VISA DOMESTIC |  |  |  | TC-309 | To check if accounting entries and GL posting are appropriate for DOCP-PURCHASE CHGBK VISA DOMESTIC |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
310 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE CHGBK MASTER INTERNATIONAL |  |  |  | TC-310 | To check if accounting entries and GL posting are appropriate for IOCP-PURCHASE CHGBK MASTER INTERNATIONAL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
311 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE REV INW MERC TRANS VISA DOMEST |  |  |  | TC-311 | To check if accounting entries and GL posting are appropriate for TDP1-PURCHASE REV INW MERC TRANS VISA DOMEST |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
312 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | REFUND CREDIT REV INW MERC VISA DOMEST |  |  |  | TC-312 | To check if accounting entries and GL posting are appropriate for TDP2-REFUND CREDIT REV INW MERC VISA DOMEST |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
313 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | CASH ADV APX REV INPUT ACQ VISA DOMEST |  |  |  | TC-313 | To check if accounting entries and GL posting are appropriate for TDP5-CASH ADV APX REV INPUT ACQ VISA DOMEST |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
314 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | CASH ADV APX INW MER TRANS VISA DOMEST |  |  |  | TC-314 | To check if accounting entries and GL posting are appropriate for TDPA-CASH ADV APX INW MER TRANS VISA DOMEST |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
315 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE INW MERCH TRAN VISA DOMESTIC |  |  |  | TC-315 | To check if accounting entries and GL posting are appropriate for TDPP-PURCHASE INW MERCH TRAN VISA DOMESTIC |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
316 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | REFUND CREDIT INW MER TRANS VISA DOM |  |  |  | TC-316 | To check if accounting entries and GL posting are appropriate for TDPR-REFUND CREDIT INW MER TRANS VISA DOM |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
317 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE REV INW MERC TRANS MAST INTL |  |  |  | TC-317 | To check if accounting entries and GL posting are appropriate for TIP1-PURCHASE REV INW MERC TRANS MAST INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
318 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | REFUND CREDIT REV INW MER MAST INTL |  |  |  | TC-318 | To check if accounting entries and GL posting are appropriate for TIP2-REFUND CREDIT REV INW MER MAST INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
319 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | CASH ADV APX REV INP ACQUIRER MAST INTL |  |  |  | TC-319 | To check if accounting entries and GL posting are appropriate for TIP5-CASH ADV APX REV INP ACQUIRER MAST INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
320 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | CASH ADV APX INW MER TRANS MAST INTL |  |  |  | TC-320 | To check if accounting entries and GL posting are appropriate for TIPA-CASH ADV APX INW MER TRANS MAST INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-13 | 2021-12-13 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
321 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE INW MERCH TRANS MASTER INTL |  |  |  | TC-321 | To check if accounting entries and GL posting are appropriate for TIPP-PURCHASE INW MERCH TRANS MASTER INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
322 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | REFUND CREDIT INW MER TRANS MAST INTL |  |  |  | TC-322 | To check if accounting entries and GL posting are appropriate for TIPR-REFUND CREDIT INW MER TRANS MAST INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
323 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE REV INW MER TRANS MAST DOMEST |  |  |  | TC-323 | To check if accounting entries and GL posting are appropriate for TMP1-PURCHASE REV INW MER TRANS MAST DOMEST |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
324 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | REFUND CREDIT REV INW MER MAST DOMEST |  |  |  | TC-324 | To check if accounting entries and GL posting are appropriate for TMP2-REFUND CREDIT REV INW MER MAST DOMEST |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
325 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | CASH ADV APX INW MERC TRANS MAST DOME |  |  |  | TC-325 | To check if accounting entries and GL posting are appropriate for TMPA-CASH ADV APX INW MERC TRANS MAST DOME |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
326 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE INW MERCH TRAN MASTER DOMESTIC |  |  |  | TC-326 | To check if accounting entries and GL posting are appropriate for TMPP-PURCHASE INW MERCH TRAN MASTER DOMESTIC |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
327 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | REFUND CREDIT INW MER TRANS MAST DOMEST |  |  |  | TC-327 | To check if accounting entries and GL posting are appropriate for TMPR-REFUND CREDIT INW MER TRANS MAST DOMEST |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
328 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE REV INW MERC TRANS VISA INTL |  |  |  | TC-328 | To check if accounting entries and GL posting are appropriate for TVP1-PURCHASE REV INW MERC TRANS VISA INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
329 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | CASH ADV APX REV INP ACQUIRER VISA INTL |  |  |  | TC-329 | To check if accounting entries and GL posting are appropriate for TVP5-CASH ADV APX REV INP ACQUIRER VISA INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
330 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | CASH ADV APX INW MER TRANS VISA INTL |  |  |  | TC-330 | To check if accounting entries and GL posting are appropriate for TVPA-CASH ADV APX INW MER TRANS VISA INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
331 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE INW MERCH TRANS VISA INTL |  |  |  | TC-331 | To check if accounting entries and GL posting are appropriate for TVPP-PURCHASE INW MERCH TRANS VISA INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
332 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | REFUND CREDIT INW MER TRANS VISA INTL |  |  |  | TC-332 | To check if accounting entries and GL posting are appropriate for TVPR-REFUND CREDIT INW MER TRANS VISA INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
333 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | PURCHASE CHGBK VISA INTERNATIONAL |  |  |  | TC-333 | To check if accounting entries and GL posting are appropriate for VOCP-PURCHASE CHGBK VISA INTERNATIONAL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
334 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | REPRESENT PUR INWARD EXCEPTION VISA DOME |  |  |  | TC-334 | To check if accounting entries and GL posting are appropriate for XDRP-REPRESENT PUR INWARD EXCEPTION VISA DOME |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
335 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | REPRESENT PUR INWARD EXCEPTION MAST INTL |  |  |  | TC-335 | To check if accounting entries and GL posting are appropriate for XIRP-REPRESENT PUR INWARD EXCEPTION MAST INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
336 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | REPRESENT PUR INWARD EXCEPTION VISA INTL |  |  |  | TC-336 | To check if accounting entries and GL posting are appropriate for XVRP-REPRESENT PUR INWARD EXCEPTION VISA INTL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
337 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | APX/CASH WITHDRAWAL |  |  |  | TC-337 | To check if accounting entries and GL posting are appropriate for 420-APX/CASH WITHDRAWAL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-14 | 2021-12-14 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
338 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | APX/APX DEBIT REVERSAL |  |  |  | TC-338 | To check if accounting entries and GL posting are appropriate for 424-APX/APX DEBIT REVERSAL. |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
339 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | APX/CREDIT REVERSAL |  |  |  | TC-339 | To check if accounting entries and GL posting are appropriate for 404-APX/CREDIT REVERSAL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
340 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | APX/REFUND |  |  |  | TC-340 | To check if accounting entries and GL posting are appropriate for 410-APX/REFUND. |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
341 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | APX/APX DEBIT REVERSAL |  |  |  | TC-341 | To check if accounting entries and GL posting are appropriate for 424-APX/APX DEBIT REVERSAL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
342 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | APX/PURCHASE |  |  |  | TC-342 | To check if accounting entries and GL posting are appropriate for 425-APX/PURCHASE. |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
343 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | APX/REFUND |  |  |  | TC-343 | To check if accounting entries and GL posting are appropriate for 410-APX/REFUND |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
344 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | APX/APX DEBIT REVERSAL |  |  |  | TC-344 | To check if accounting entries and GL posting are appropriate for 424-APX/APX DEBIT REVERSAL. |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
345 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | APX/PURCHASE |  |  |  | TC-345 | To check if accounting entries and GL posting are appropriate for 425-APX/PURCHASE |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
346 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | MADA E-COMMERCE PURCHASE REVERSAL |  |  |  | TC-346 | To check if accounting entries and GL posting are appropriate for 444-MADA E-COMMERCE PURCHASE REVERSAL |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
347 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | MADA E-COMMERCE PURCHASE |  |  |  | TC-347 | To check if accounting entries and GL posting are appropriate for 445-MADA E-COMMERCE PURCHASE |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
348 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | MADA - ECOMMERCE REFUND |  |  |  | TC-348 | To check if accounting entries and GL posting are appropriate for 446-MADA - ECOMMERCE REFUND |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
349 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | APX/REFUND - GCC - ACQUIRER |  |  |  | TC-349 | To check if accounting entries and GL posting are appropriate for 610-APX/REFUND - GCC - ACQUIRER |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
350 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | APX DEBIT REVERSAL - GCC - ACQUIRER |  |  |  | TC-350 | To check if accounting entries and GL posting are appropriate for 624-APX DEBIT REVERSAL - GCC - ACQUIRER |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
351 | UAT - Apex | Apex Execution R2 | Accounting entries & GL posting |  |  | APX/PURCHASE GCC - ACQUIRER |  |  |  | TC-351 | To check if accounting entries and GL posting are appropriate for 625-APX/PURCHASE GCC - ACQUIRER |  |  |  | Accounting entries should be mapped appropriately and posted to FAH successfully |  |  | Business - Maveric |  |  | 2021-12-15 | 2021-12-15 |  |  | UNEXECUTED | [6 empty] | Arsalan | BSF IT | Require Open2 Migrated Transaction Data and Migrated Merchant Data - Awaiting Approval from Different BSF Departments | 1 | 0 | 0% | 0% | Pending | W17
Formulas:
Plan Duration = NETWORKDAYS.INTL(Table4871015[[#This Row],[Plan St Date]],Table4871015[[#This Row],[Plan End Date]],7)
Plan Burnt = IF(Table4871015[[#This Row],[Plan St Date]]<=W1,NETWORKDAYS.INTL(Table4871015[[#This Row],[Plan St Date]],W1,7),0)
Week # = "W"&WEEKNUM(Table4871015[[#This Row],[Plan End Date]])-34
Completion Week # = IF(Table4871015[[#This Row],[Completion Date]]<>"","W"&(WEEKNUM(Table4871015[[#This Row],[Completion Date]])-24),"")